## Dashboard
|  |  | Weekly Contract Package Dashboard | [14 empty] | PROGRAM |  |  |  | PROJECT |  | PACKAGE |  | CONTRACTOR |  |  |  | PROJECT DIRECTOR |  |  | 935 | 942
[18 empty] | AMAALA |  |  |  | Triple Bay Early Earth Works (Marina) |  | 1100101 |  | Hasco |  |  |  | AMAALA Delivery Director Name |  |  | 0 | 0
V8.9
[5 empty] | Data Cutoff: |  |  | 2022-05-12 | [24 empty] | 0% | 0%
Contract Timeline | [7 empty] | Overall Progress | [10 empty] | Direct Manpower
[35 empty] | This Week Manpower |  |  | Planned |  |  | Actual |  | Variance
[38 empty] | 65 |  |  | 79 |  | 14
Reason for Variance:
RAF BUILDING DEMOLITION WORK STARTED
[8 empty] | Last Week |  |  |  | This Week |  |  | Weekly progress
[8 empty] | Plan |  | 97.44% |  | 98.63% |  |  | 0.5936%
[8 empty] | Actual |  | 86.83% |  | 87.42%
[8 empty] | Variance |  | -10.61% |  | -11.21% |  |  | 236633.99
Escalation - Issue & Actions
# | Issue |  |  | Required Action | [6 empty] | Owner |  | Target Date |  | This Week Actual/ Forecast Date |  | Weekly Trend
-59
1 | Approval to demolish of Royal Saudi airforce Buildings |  |  | AMAAALA Approved to Start the Demolition of RAF Building | [6 empty] | AMAALA |  | 4468500% |  | 4474600% |  | 61
Cashflow( Certified Amount), Variations, & KPI
[35 empty] | % Increase in Contract Vaule | [5 empty] | % Certified to Date (inc. advance)
[35 empty] | 36.66% | [5 empty] | 118.2%
Variance & KPI's
[35 empty] | SV |  | -4.3097 |  |  |  | SPI | 0.9
[35 empty] | CV |  | 10098 |  |  |  | CPI | 1
Progress S Curve & Variance Analysis
-
Weekly Average Actual Last 2 Months
[19 empty] | Cumulative (Milion SAR) |  |  |  | Planned | 39.3165 | 98.63% |  | Top 3 Early Warnings & Potential Cost Impact
0.7157%
[23 empty] | Actual | 35.0068 | 87.42% |  | # | Description | [8 empty] | Cost (Million Sar) |  |  | Time (Days) |  | Status
[27 empty] | 1 | Hasco Submitted Revised Baseline Programme | [8 empty] | 39872540 |  |  | 2022-05-31
Weekly Average Plan Next 2 Months
[23 empty] | Variance | -4.3097 | 11.21% |  | 2
3
1.2%
-
3 Months Look Ahead AMAALA Planned (Million SAR)
[21 empty] | 2022-03-30 | [5 empty] | 2022-04-30 | [6 empty] | 2022-05-31
[19 empty] | Plan |  | 2022-05-17 |  | Cutting Around RSMLI |  |  |  | 2022-05-17 |  | Cutting Around RSMLI |  |  |  |  | 2022-07-11 |  | Demolish of unused coastgaurd
[19 empty] | Forecast |  | 2022-05-17 |  | Excavation & Transportation to stock pile location within 3 Km of TB area for Around RSMLI Building |  |  |  | 2022-05-18 |  | Excavation & Transportation to stock pile location within 3 Km of TB area for Around RSMLI Building |  |  |  |  | 2022-07-13 |  | Excavation & Transportation to stock pile location within 3 Km of TB area for under RAF, Air force Office ,& Around RSMLI Building ( Forecast Finish Date)
[9 empty] | Top Contributors to the variance |  |  |  |  | -100% |  |  |  |  | Variance |  | 0 | [5 empty] | 1 | [6 empty] | 2
[6 empty] | Construction |  |  | -9.437%
Look Ahead - Major Activties & Milestones
[6 empty] | Procurement | 2.5 |  | 0% | [9 empty] | # | Description | [8 empty] | Activities/ Interface |  | Plan Date | Last Week Actual/ Update |  |  | This Week Actual/ Update |  |  |  | Variance From Plan |  |  | Weekly Trend
1
[6 empty] | 1 | [12 empty] | 1 | Access Road Maintainance | [8 empty] | Activity |  | 4462000% | 94.61% |  |  | 94.61% | [6 empty] | 0
[6 empty] | Engineering |  |  | 0% | [9 empty] | 2 | Cutting p1 &2 - Ripping Consolidated Material around RSMLI Building Area | [8 empty] | Activity |  | 4463300% | 100% |  |  | 100% | [6 empty] | 0
[6 empty] | 1 | [12 empty] | 3 | Cutting 1& 2 - Heavy Breaking of Rock around RSMLI Building Area | [8 empty] | Activity |  | 4463300% | 100% |  |  | 100% | [6 empty] | 0
[6 empty] | 1 | [12 empty] | 4 | Cutting 3 & 4 - Heavy Breaking of Rock around RSMLI Building Area | [8 empty] | Activity |  | 30/03/2022 | 50% |  |  | 80%
[6 empty] | Prelims |  |  | -14.32% | [9 empty] | 5 | Cutting p3 & 4 - Ripping Consolidated Material around RSMLI Building Area | [8 empty] | Activity |  | 30/03/2022 | 50% |  |  | 80%
[19 empty] | 6 | Cutting p5 & 6 - Ripping Consolidated Material around RSMLI Building Area | [8 empty] | Activity |  | 4465500% | 80% |  |  | 80%
[6 empty] | 1 | [12 empty] | 7 | Priority 5 & 6 - Heavy Breaking of Rock around RSMLI Building Area | [8 empty] | Activity |  | 4465500% | 80% |  |  | 80%
Proposed Mitigations to Recover Variance |  | Finalize of required permits to open the Pending work for Hasco/ Hasco to submit Revised program showing the required resources to finish the remaining works on time and work at site accordingly | [16 empty] | 8 | Priority 7 & 8 - Ripping Consolidated Material around RSMLI Building Area | [8 empty] | Activity |  | 4467500% | 0.5 |  |  | 50%
Schedule
Cashflow
EAC*
Last Period
This Period
Up to 14 days slippage
15 to 42 days slippage
more than 42 slippage
< 95% FC achieved
0.94% to 0.85%FC achieved
>0.85%FC achieved
>10% Var. contract
11% to >19% Var. contract
>20% Var. contract
RAG Status Legend
*EAC includes PBIs

## Overall
Report Week Date (first day of the reported week)
2022-05-12
Data Cutoff | 2022-05-12
Asset Information |  |  |  |  | Schedule | Overall Progress |  | Variance
Program | Project | Package | Contractor | Construction Director | EOT # 05 Finish Date | Planned Progress | Actual Progress
Amalla | Triple Bay Early Earth Works (Marina) | 1100101 | Hasco | AMAALA Delivery Director Name | 2022-05-31 | 98.63% | 87.42% | -11.21%
[6 empty] | 1.368% | 12.58%
0.6097

## Contract Timeline
Report Week Date
2022-05-12
[16 empty] | 935 | 942
Start Date | Baseline Finish Date | Forecast End Date | EOT-01 | EOT-02 | Anticipated Length (weeks) | Critical Path Updates | Veriance Justification | Variance
2019-06-23 | 2021-01-31 | 2022-05-31 | 2021-03-31 | 2021-11-30 | 153.2857 |  |  | -485 |  | Last Report Date | This Report Date | Last Period Updated Date | This Period Updated Finish Date | Last Period Variance | This Period Variance | Last | This
[9 empty] | 0 |  | 4363900% | 0 | 4363900% | 0 | 0 | 0 | 0
title | supporting data | duration | Start | Finish | discription |  |  |  | 0 | 4364300% | 4365000% | 4364300% | 4365000% | 0 | 11 | 0 | 11
Base Line | 44228 | 589 | 2019-06-23 | 2021-01-31 | Contractual Duration |  |  |  | 0 | 4365000% | 4365700% | 4365000% | 4365700% | 11 | 18 | 11 | 18
EOT No.1 | 59 | 59 | 2021-01-31 | 2021-03-31 | EOT No.1 |  |  |  | 0 | 4365700% | 4366400% | 4365700% | 4366400% | 18 | 25 | 18 | 25
EOT No.2 | 64 | 64 | 2021-03-31 | 2021-06-03 | EOT No.2 | 588 |  |  | 0 | 4366400% | 4367100% | 4366400% | 4367100% | 25 | 32 | 25 | 32
EOT NO.3 | 180 | 180 | 2021-06-03 | 2021-11-30 | EOT NO.3 |  |  |  | 0 | 4367100% | 4367800% | 4367100% | 4367800% | 32 | 39 | 32 | 39
EOT No. 04 | 90 | 90 | 2021-12-01 | 2022-02-28 | EOT No.4 |  |  |  | 0 | 4367800% | 4368500% | 4367800% | 4368500% | 39 | 46 | 39 | 46
Forecast End date | 92 | 92 | 2022-03-01 | 2022-05-31 | Forecast End data |  |  |  | 0 | 4368500% | 4369200% | 4368500% | 4369200% | 46 | 53 | 46 | 53
[9 empty] | 0 | 4369200% | 4369900% | 4369200% | 4369900% | 53 | 60 | 53 | 60
[9 empty] | 0 | 4369900% | 4370600% | 4369900% | 4370600% | 60 | 67 | 60 | 67
[9 empty] | 0 | 4370600% | 4371300% | 4370600% | 4371300% | 67 | 74 | 67 | 74
[9 empty] | 0 | 4371300% | 4372000% | 4371300% | 4372000% | 74 | 81 | 74 | 81 | 545 | 150 | EOT No. 3
Project Time Line | [8 empty] | 0 | 4372000% | 4372700% | 4372000% | 4372700% | 81 | 88 | 81 | 88 | 485 | 60 | EOT No. 2
[9 empty] | 0 | 4372700% | 4373400% | 4372700% | 4373400% | 88 | 95 | 88 | 95 | 365 | 120 | EOT No. 1
[9 empty] | 0 | 4373400% | 4374100% | 4373400% | 4374100% | 95 | 102 | 95 | 102 | 0 | 365 | Baseline
[9 empty] | 0 | 4374100% | 4374800% | 4374100% | 4374800% | 102 | 109 | 102 | 109
[9 empty] | 0 | 4374800% | 4375500% | 4374800% | 4375500% | 109 | 116 | 109 | 116
[9 empty] | 0 | 4375500% | 4376200% | 4375500% | 4376200% | 116 | 123 | 116 | 123
[9 empty] | 0 | 4376200% | 4376900% | 4376200% | 4376900% | 123 | 130 | 123 | 130
[9 empty] | 0 | 4376900% | 4377600% | 4376900% | 4377600% | 130 | 137 | 130 | 137
[9 empty] | 0 | 4377600% | 4378300% | 4377600% | 4378300% | 137 | 144 | 137 | 144
[9 empty] | 0 | 4378300% | 4379000% | 4378300% | 4379000% | 144 | 151 | 144 | 151
[9 empty] | 0 | 4379000% | 4379700% | 4379000% | 4379700% | 151 | 158 | 151 | 158
[9 empty] | 0 | 4379700% | 4380400% | 4379700% | 4380400% | 158 | 165 | 158 | 165
| 4422800% | [7 empty] | 0 | 4380400% | 4381100% | 4380400% | 4381100% | 165 | 172 | 165 | 172
[9 empty] | 0 | 4381100% | 4381800% | 4381100% | 4381800% | 172 | 179 | 172 | 179
| 44227 | [7 empty] | 0 | 4381800% | 4382500% | 4381800% | 4382500% | 179 | 186 | 179 | 186
| 4422700% | [7 empty] | 0 | 4382500% | 4383200% | 4382500% | 4383200% | 186 | 193 | 186 | 193
[9 empty] | 0 | 4383200% | 4383900% | 4383200% | 4383900% | 193 | 200 | 193 | 200
[9 empty] | 0 | 4383900% | 4384600% | 4383900% | 4384600% | 200 | 207 | 200 | 207
[9 empty] | 0 | 4384600% | 4385300% | 4384600% | 4385300% | 207 | 214 | 207 | 214
[9 empty] | 0 | 4385300% | 4386000% | 4385300% | 4386000% | 214 | 221 | 214 | 221
[9 empty] | 0 | 4386000% | 4386700% | 4386000% | 4386700% | 221 | 228 | 221 | 228
[9 empty] | 0 | 4386700% | 4387400% | 4386700% | 4387400% | 228 | 235 | 228 | 235
[9 empty] | 0 | 4387400% | 4388100% | 4387400% | 4388100% | 235 | 242 | 235 | 242
[9 empty] | 0 | 4388100% | 4388800% | 4388100% | 4388800% | 242 | 249 | 242 | 249
[9 empty] | 0 | 4388800% | 4389500% | 4388800% | 4389500% | 249 | 256 | 249 | 256
[9 empty] | 0 | 4389500% | 4390200% | 4389500% | 4390200% | 256 | 263 | 256 | 263
[9 empty] | 0 | 4390200% | 4390900% | 4390200% | 4390900% | 263 | 270 | 263 | 270
[9 empty] | 0 | 4390900% | 4391600% | 4390900% | 4391600% | 270 | 277 | 270 | 277
[9 empty] | 0 | 4391600% | 4392300% | 4391600% | 4392300% | 277 | 284 | 277 | 284
[9 empty] | 0 | 4392300% | 4393000% | 4392300% | 4393000% | 284 | 291 | 284 | 291
[9 empty] | 0 | 4393000% | 4393700% | 4393000% | 4393700% | 291 | 298 | 291 | 298
[9 empty] | 0 | 4393700% | 4394400% | 4393700% | 4394400% | 298 | 305 | 298 | 305
[9 empty] | 0 | 4394400% | 4395100% | 4394400% | 4395100% | 305 | 312 | 305 | 312
[9 empty] | 0 | 4395100% | 4395800% | 4395100% | 4395800% | 312 | 319 | 312 | 319
[9 empty] | 0 | 4395800% | 4396500% | 4395800% | 4396500% | 319 | 326 | 319 | 326
[9 empty] | 0 | 4396500% | 4397200% | 4396500% | 4397200% | 326 | 333 | 326 | 333
[9 empty] | 0 | 4397200% | 4397900% | 4397200% | 4397900% | 333 | 340 | 333 | 340
[9 empty] | 0 | 4397900% | 4398600% | 4397900% | 4398600% | 340 | 347 | 340 | 347
[9 empty] | 0 | 4398600% | 4399300% | 4398600% | 4399300% | 347 | 354 | 347 | 354
[9 empty] | 0 | 4399300% | 4400000% | 4399300% | 4400000% | 354 | 361 | 354 | 361
[9 empty] | 0 | 4400000% | 4400700% | 4400000% | 4400700% | 361 | 368 | 361 | 368
[9 empty] | 0 | 4400700% | 4401400% | 4400700% | 4401400% | 368 | 375 | 368 | 375
[9 empty] | 0 | 4401400% | 4402100% | 4401400% | 4402100% | 375 | 382 | 375 | 382
[9 empty] | 0 | 4402100% | 4402800% | 4402100% | 4402800% | 382 | 389 | 382 | 389
[9 empty] | 0 | 4402800% | 4403500% | 4402800% | 4403500% | 389 | 396 | 389 | 396
[9 empty] | 0 | 4403500% | 4404200% | 4403500% | 4404200% | 396 | 403 | 396 | 403
[9 empty] | 0 | 4404200% | 4404900% | 4404200% | 4404900% | 403 | 410 | 403 | 410
[9 empty] | 0 | 4404900% | 4405600% | 4404900% | 4405600% | 410 | 417 | 410 | 417
[9 empty] | 0 | 4405600% | 4406300% | 4405600% | 4406300% | 417 | 424 | 417 | 424
[9 empty] | 0 | 4406300% | 4407000% | 4406300% | 4407000% | 424 | 431 | 424 | 431
[9 empty] | 0 | 4407000% | 4407700% | 4407000% | 4407700% | 431 | 438 | 431 | 438
[9 empty] | 0 | 4407700% | 4408400% | 4407700% | 4408400% | 438 | 445 | 438 | 445
[9 empty] | 0 | 4408400% | 4409100% | 4408400% | 4409100% | 445 | 452 | 445 | 452
[9 empty] | 0 | 4409100% | 4409800% | 4409100% | 4409800% | 452 | 459 | 452 | 459
[9 empty] | 0 | 4409800% | 4410500% | 4409800% | 4410500% | 459 | 466 | 459 | 466
[9 empty] | 0 | 4410500% | 4411200% | 4410500% | 4411200% | 466 | 473 | 466 | 473
[9 empty] | 0 | 4411200% | 4411900% | 4411200% | 4411900% | 473 | 480 | 473 | 480
[9 empty] | 0 | 4411900% | 4412600% | 4411900% | 4412600% | 480 | 487 | 480 | 487
[9 empty] | 0 | 4412600% | 4413300% | 4412600% | 4413300% | 487 | 494 | 487 | 494
[9 empty] | 0 | 4413300% | 4414000% | 4413300% | 4414000% | 494 | 501 | 494 | 501
[9 empty] | 0 | 4414000% | 4414700% | 4414000% | 4414700% | 501 | 508 | 501 | 508
[9 empty] | 0 | 4414700% | 4415400% | 4414700% | 4415400% | 508 | 515 | 508 | 515
[9 empty] | 0 | 4415400% | 4416100% | 4415400% | 4416100% | 515 | 522 | 515 | 522
[9 empty] | 0 | 4416100% | 4416800% | 4416100% | 4416800% | 522 | 529 | 522 | 529
[9 empty] | 0 | 4416800% | 4417500% | 4416800% | 4417500% | 529 | 536 | 529 | 536
[9 empty] | 0 | 4417500% | 4418200% | 4417500% | 4418200% | 536 | 543 | 536 | 543
[9 empty] | 0 | 4418200% | 4418900% | 4418200% | 4418900% | 543 | 550 | 543 | 550
[9 empty] | 0 | 4418900% | 4419600% | 4418900% | 4419600% | 550 | 557 | 550 | 557
[9 empty] | 0 | 4419600% | 4420300% | 4419600% | 4420300% | 557 | 564 | 557 | 564
[9 empty] | 0 | 4420300% | 4421000% | 4420300% | 4421000% | 564 | 571 | 564 | 571
[9 empty] | 0 | 4421000% | 4421700% | 4421000% | 4421700% | 571 | 578 | 571 | 578
[9 empty] | 0 | 4421700% | 4422400% | 4421700% | 4422400% | 578 | 585 | 578 | 585
[9 empty] | 0 | 4422400% | 4423100% | 4422400% | 4423100% | 585 | 592 | 585 | 592
[9 empty] | 0 | 4423100% | 4423800% | 4423100% | 4423800% | 592 | 599 | 592 | 599
[9 empty] | 0 | 4423800% | 4424500% | 4423800% | 4424500% | 599 | 606 | 599 | 606
[9 empty] | 0 | 4424500% | 4425200% | 4424500% | 4425200% | 606 | 613 | 606 | 613
[9 empty] | 0 | 4425200% | 4425900% | 4425200% | 4425900% | 613 | 620 | 613 | 620
[9 empty] | 0 | 4425900% | 4426600% | 4425900% | 4426600% | 620 | 627 | 620 | 627
[9 empty] | 0 | 4426600% | 4427300% | 4426600% | 4427300% | 627 | 634 | 627 | 634
[9 empty] | 0 | 4427300% | 4428000% | 4427300% | 4428000% | 634 | 641 | 634 | 641
[9 empty] | 0 | 4428000% | 4428700% | 4428000% | 4428700% | 641 | 648 | 641 | 648
[9 empty] | 0 | 4428700% | 4429400% | 4428700% | 4429400% | 648 | 655 | 648 | 655
[9 empty] | 0 | 4429400% | 4430100% | 4429400% | 4430100% | 655 | 662 | 655 | 662
[9 empty] | 0 | 4430100% | 4430800% | 4430100% | 4430800% | 662 | 669 | 662 | 669
[9 empty] | 0 | 4430800% | 4431500% | 4430800% | 4431500% | 669 | 676 | 669 | 676
[9 empty] | 0 | 4431500% | 4432200% | 4431500% | 4432200% | 676 | 683 | 676 | 683
[9 empty] | 0 | 4432200% | 4432900% | 4432200% | 4432900% | 683 | 690 | 683 | 690
[9 empty] | 0 | 4432900% | 4433600% | 4432900% | 4433600% | 690 | 697 | 690 | 697
[9 empty] | 0 | 4433600% | 4434300% | 4433600% | 4434300% | 697 | 704 | 697 | 704
[9 empty] | 0 | 4434300% | 4435000% | 4434300% | 4435000% | 704 | 711 | 704 | 711
[9 empty] | 0 | 4435000% | 4435700% | 4435000% | 4435700% | 711 | 718 | 711 | 718
[9 empty] | 0 | 4435700% | 4436400% | 4435700% | 4436400% | 718 | 725 | 718 | 725
[9 empty] | 0 | 4436400% | 4437100% | 4436400% | 4437100% | 725 | 732 | 725 | 732
[9 empty] | 0 | 4437100% | 4437800% | 4437100% | 4437800% | 732 | 739 | 732 | 739
[9 empty] | 0 | 4437800% | 4438500% | 4437800% | 4438500% | 739 | 746 | 739 | 746
[9 empty] | 0 | 4438500% | 4439200% | 4438500% | 4439200% | 746 | 753 | 746 | 753
[9 empty] | 0 | 4439200% | 4439900% | 4439200% | 4439900% | 753 | 760 | 753 | 760
[9 empty] | 0 | 4439900% | 4440600% | 4439900% | 4440600% | 760 | 767 | 760 | 767
[9 empty] | 0 | 4440600% | 4441300% | 4440600% | 4441300% | 767 | 774 | 767 | 774
[9 empty] | 0 | 4441300% | 4442000% | 4441300% | 4442000% | 774 | 781 | 774 | 781
[9 empty] | 0 | 4442000% | 4442700% | 4442000% | 4442700% | 781 | 788 | 781 | 788
[9 empty] | 0 | 4442700% | 4443400% | 4442700% | 4443400% | 788 | 795 | 788 | 795
[9 empty] | 0 | 4443400% | 4444100% | 4443400% | 4444100% | 795 | 802 | 795 | 802
[9 empty] | 0 | 4444100% | 4444800% | 4444100% | 4444800% | 802 | 809 | 802 | 809
[9 empty] | 0 | 4444800% | 4445500% | 4444800% | 4445500% | 809 | 816 | 809 | 816
[9 empty] | 0 | 4445500% | 4446200% | 4445500% | 4446200% | 816 | 823 | 816 | 823
[9 empty] | 0 | 4446200% | 4446900% | 4446200% | 4446900% | 823 | 830 | 823 | 830
[9 empty] | 0 | 4446900% | 4447600% | 4446900% | 4447600% | 830 | 837 | 830 | 837
[9 empty] | 0 | 4447600% | 4448300% | 4447600% | 4448300% | 837 | 844 | 837 | 844
[9 empty] | 0 | 4448300% | 4449000% | 4448300% | 4449000% | 844 | 851 | 844 | 851
[9 empty] | 0 | 4449000% | 4449700% | 4449000% | 4449700% | 851 | 858 | 851 | 858
[9 empty] | 0 | 4449700% | 4450400% | 4449700% | 4450400% | 858 | 865 | 858 | 865
[9 empty] | 0 | 4450400% | 4451100% | 4450400% | 4451100% | 865 | 872 | 865 | 872
[9 empty] | 0 | 4451100% | 4451800% | 4451100% | 4451800% | 872 | 879 | 872 | 879
[9 empty] | 0 | 4451800% | 4452500% | 4451800% | 4452500% | 879 | 886 | 879 | 886
[9 empty] | 0 | 4452500% | 4453200% | 4452500% | 4453200% | 886 | 893 | 886 | 893
[9 empty] | 0 | 4453200% | 4453900% | 4453200% | 4453900% | 893 | 900 | 893 | 900
[9 empty] | 0 | 4453900% | 4454600% | 4453900% | 4454600% | 900 | 907 | 900 | 907
[9 empty] | 0 | 4454600% | 4455300% | 4454600% | 4455300% | 907 | 914 | 907 | 914
[9 empty] | 0 | 4455300% | 4456000% | 4455300% | 4456000% | 914 | 921 | 914 | 921
[9 empty] | 0 | 4456000% | 4456700% | 4456000% | 4456700% | 921 | 928 | 921 | 928
[9 empty] | 0 | 4456700% | 4457400% | 4456700% | 4457400% | 928 | 935 | 928 | 935
[9 empty] | 0 | 4457400% | 4458100% | 4457400% | 4458100% | 935 | 942 | 935 | 942
0
0
0
0
0
0
Formulas:
EOT-01 = [EOT-02, row above]
EOT-01 = [EOT-02, row above]+1
EOT-02 = [EOT-01]+[Forecast End Date]-1
EOT-02 = [EOT-01]+[Forecast End Date]
Anticipated Length (weeks) = DAYS(Timeline[Forecast End Date],Timeline[Start Date])/7
Variance = DAYS(Timeline[Baseline Finish Date],Timeline[Forecast End Date])
Contractual Duration
EOT No.1
EOT No.2
EOT NO.3
EOT No.4
FORECAST DATE

## OverAll S-Curve
[8 empty] | Report Week Date |  |  | SPI | 106.7%
|  | OverAll S CURVE ¦ DATA INPUT | [5 empty] | 2022-05-12
|  | Date | Weekly Plan | Weekly Actual | Cumulative Plan | Cumulative Actual |  | Weekly Average Actual Last 2 Months |  |  |  | Weekly Average Plan Next 2 Months |  |  |  |  | Requirment to Meet Plan
| 0 | 2019-06-23 | 0% | 0% | 0% | 0% |  | 0.5084% |  |  |  | 0.8246% |  |  |  |  | 0.93754
| 0 | 2019-06-27 | 0.3934% | 0.06157% | 0.3934% | 0.06157%
| 0 | 2019-07-04 | 0.4817% | 0.07542% | 0.8751% | 0.137%
| 0 | 2019-07-11 | 0.4816% | 0.0753% | 1.357% | 0.2123%
| 0 | 2019-07-18 | 0.5293% | 0.1139% | 1.886% | 0.3262%
| 0 | 2019-07-25 | 0.5811% | 0.156% | 2.467% | 0.4822%
| 0 | 2019-08-01 | 0.5759% | 0.1786% | 3.043% | 0.6608%
| 0 | 2019-08-08 | 0.5276% | 0.1301% | 3.571% | 0.7908%
| 0 | 2019-08-15 | 0.1279% | 0.02326% | 3.699% | 0.8141%
| 0 | 2019-08-22 | 0.8221% | 0.1864% | 4.521% | 1%
| 0 | 2019-08-29 | 0.8993% | 0.2514% | 5.42% | 1.252%
| 0 | 2019-09-05 | 1.328% | 0.5986% | 6.748% | 1.85%
| 0 | 2019-09-12 | 1.507% | 0.7604% | 8.255% | 2.611%
| 0 | 2019-09-19 | 1.227% | 0.8038% | 9.481% | 3.415%
| 0 | 2019-09-26 | 0.6469% | 0.4357% | 10.13% | 3.85%
| 0 | 2019-10-03 | 0.7766% | 0.2985% | 10.9% | 4.149%
| 0 | 2019-10-10 | 0.7771% | 0.299% | 11.68% | 4.448%
| 0 | 2019-10-17 | 0.7784% | 0.2999% | 12.46% | 4.748%
| 0 | 2019-10-24 | 0.7631% | 0.2999% | 13.22% | 5.048%
| 0 | 2019-10-31 | 0.7443% | 0.2999% | 13.97% | 5.348%
| 0 | 2019-11-07 | 0.7443% | 0.2999% | 14.71% | 5.647%
| 0 | 2019-11-14 | 0.7431% | 0.3001% | 15.46% | 5.947%
| 0 | 2019-11-21 | 0.6625% | 0.3008% | 16.12% | 6.248%
| 0 | 2019-11-28 | 0.663% | 0.301% | 16.78% | 6.549%
| 0 | 2019-12-05 | 0.669% | 0.2953% | 17.45% | 6.845%
| 0 | 2019-12-12 | 0.6802% | 0.2509% | 18.13% | 7.096%
| 0 | 2019-12-19 | 0.673% | 0.251% | 18.8% | 7.347%
| 0 | 2019-12-26 | 0.6544% | 0.2401% | 19.46% | 7.587%
| 0 | 2020-01-02 | 0.3945% | 0.2344% | 19.85% | 7.821%
| 0 | 2020-01-09 | 0.182% | 0.2346% | 20.03% | 8.056%
| 0 | 2020-01-16 | 0.2227% | 0.2697% | 20.26% | 8.325%
| 0 | 2020-01-23 | 0.3207% | 0.3633% | 20.58% | 8.689%
| 0 | 2020-01-30 | 0.2517% | 0.3449% | 20.83% | 9.034%
| 0 | 2020-02-06 | 0.1733% | 0.2537% | 21% | 9.287%
| 0 | 2020-02-13 | 0.3352% | 0.3941% | 21.34% | 9.681%
| 0 | 2020-02-20 | 1.068% | 0.9501% | 22.41% | 10.63%
| 0 | 2020-02-27 | 1.419% | 1.364% | 23.82% | 12%
| 0 | 2020-03-05 | 0.7855% | 0.9523% | 24.61% | 12.95%
| 0 | 2020-03-12 | 0.3242% | 0.465% | 24.93% | 13.41%
| 0 | 2020-03-19 | 0.2428% | 0.2675% | 25.18% | 13.68%
| 0 | 2020-03-26 | 0.2224% | 0.2668% | 25.4% | 13.95%
| 0 | 2020-04-02 | 0.1856% | 0.2668% | 25.59% | 14.21%
| 0 | 2020-04-09 | 0.6529% | 0.4339% | 26.24% | 14.65%
| 0 | 2020-04-16 | 0.0431% | 0.5615% | 26.28% | 15.21%
| 0 | 2020-04-23 | 0.03858% | 0.4111% | 26.32% | 15.62%
| 0 | 2020-04-30 | 0.03094% | 0.2521% | 26.35% | 15.87%
| 0 | 2020-05-07 | 1.566% | 1.018% | 27.92% | 16.89%
| 0 | 2020-05-14 | 3.565% | 1.978% | 31.48% | 18.87%
| 0 | 2020-05-21 | 3.465% | 1.493% | 34.95% | 20.36%
| 0 | 2020-05-28 | 1.76% | 0.7449% | 36.71% | 21.11%
| 0 | 2020-06-04 | 3.028% | 1.596% | 39.73% | 22.7%
| 0 | 2020-06-11 | 2.974% | 1.596% | 42.71% | 24.3%
| 0 | 2020-06-18 | 2.974% | 1.582% | 45.68% | 25.88%
| 0 | 2020-06-25 | 2.98% | 1.518% | 48.66% | 27.4%
| 0 | 2020-07-02 | 2.929% | 1.561% | 51.59% | 28.96%
| 0 | 2020-07-09 | 2.904% | 1.467% | 54.5% | 30.43%
| 0 | 2020-07-16 | 1.523% | 1.448% | 56.02% | 31.88%
| 0 | 2020-07-23 | 1.199% | 1.469% | 57.22% | 33.34%
| 0 | 2020-07-30 | 1.027% | 1.258% | 58.24% | 34.6%
| 0 | 2020-08-06 | 0.6376% | 0.7569% | 58.88% | 35.36%
| 0 | 2020-08-13 | 1.199% | 1.444% | 60.08% | 36.8%
| 0 | 2020-08-20 | 1.328% | 1.543% | 61.41% | 38.35%
| 0 | 2020-08-27 | 1.733% | 1.654% | 63.14% | 40%
| 0 | 2020-09-03 | 1.809% | 1.654% | 64.95% | 41.65%
| 0 | 2020-09-10 | 1.697% | 1.633% | 66.65% | 43.29%
| 0 | 2020-09-17 | 1.353% | 1.683% | 68% | 44.97%
| 0 | 2020-09-24 | 1.643% | 1.478% | 69.64% | 46.45%
| 0 | 2020-10-01 | 2.965% | 1.971% | 72.61% | 48.42%
| 0 | 2020-10-08 | 1.338% | 1.972% | 73.95% | 50.39%
| 0 | 2020-10-15 | 1.171% | 1.971% | 75.12% | 52.36%
| 0 | 2020-10-22 | 1.02% | 1.94% | 76.14% | 54.3%
| 0 | 2020-10-29 | 0.2651% | 1.785% | 76.4% | 56.09%
| 0 | 2020-11-05 | 0.03829% | 1.756% | 76.44% | 57.84%
| 0 | 2020-11-12 | 0.0381% | 1.755% | 76.48% | 59.6%
| 0 | 2020-11-19 | 0.1283% | 1.826% | 76.61% | 61.42%
| 0 | 2020-11-26 | 0.1293% | 1.564% | 76.74% | 62.99%
| 0 | 2020-12-03 | 0.1293% | 1.3% | 76.87% | 64.29%
| 0 | 2020-12-10 | 0.1293% | 1.3% | 77% | 65.59%
| 0 | 2020-12-17 | 0.1293% | 1.3% | 77.12% | 66.89%
| 0 | 2020-12-24 | 0.1293% | 1.214% | 77.25% | 68.1%
| 0 | 2020-12-31 | 0.1125% | 1.16% | 77.37% | 69.26%
| 0 | 2021-01-07 | 0.03764% | 0.9661% | 77.4% | 70.23%
| 0 | 2021-01-14 | 0.03764% | 0.9355% | 77.44% | 71.16%
| 0 | 2021-01-21 | 0.03764% | 0.9852% | 77.48% | 72.15%
| 0 | 2021-01-28 | 0.03764% | 0.8621% | 77.52% | 73.01%
| 0 | 2021-02-04 | 0.03764% | 0.8174% | 77.55% | 73.83%
| 0 | 2021-02-11 | 0.03764% | 0.3327% | 77.59% | 74.16%
| 0 | 2021-02-18 | 0.03764% | 0.6649% | 77.63% | 74.83%
| 0 | 2021-02-25 | 0.03764% | 1.331% | 77.67% | 76.16%
| 0 | 2021-03-04 | 0.03764% | 0.09386% | 77.71% | 76.25%
| 0 | 2021-03-11 | 0.03764% | 0.09386% | 77.74% | 76.34%
| 0 | 2021-03-18 | 0.03764% | 0.09386% | 77.78% | 76.44%
| 0 | 2021-03-25 | 0.03764% | 0.09386% | 77.82% | 76.53% |  | 23.37%
| 0 | 2021-04-01 | 0.03764% | 0.09386% | 77.86% | 76.63% |  | 137.1595
| 0 | 2021-04-08 | 0.03764% | 0.09386% | 77.89% | 76.72%
| 0 | 2021-04-15 | 0.03764% | 0.09386% | 77.93% | 76.81%
| 0 | 2021-04-22 | 0.03764% | 0.09386% | 77.97% | 76.91%
| 0 | 2021-04-29 | 0.1924% | 0.1177% | 78.16% | 77.02%
| 0 | 2021-05-06 | 0.918% | 0.4392% | 79.08% | 77.46%
| 0 | 2021-05-13 | 1.031% | 0.4392% | 80.11% | 77.9%
| 0 | 2021-05-20 | 0.4183% | 0.4392% | 80.53% | 78.34%
| 0 | 2021-05-27 | 0.03764% | 0.4392% | 80.57% | 78.78%
| 0 | 2021-06-03 | 0.03764% | 0.4392% | 80.6% | 79.22%
| 0 | 2021-06-10 | 0.03764% | 0.4177% | 80.64% | 79.64%
| 0 | 2021-06-17 | 0.03764% | 0.1176% | 80.68% | 79.76%
| 0 | 2021-06-24 | 0.03764% | 0.09386% | 80.72% | 79.85%
| 0 | 2021-07-01 | 0.03764% | 0.09386% | 80.75% | 79.94%
| 0 | 2021-07-08 | 0.03764% | 0.09386% | 80.79% | 80.04%
| 0 | 2021-07-15 | 0.03764% | 0.09386% | 80.83% | 80.13%
| 0 | 2021-07-22 | 0.01255% | 0.03129% | 80.84% | 80.16%
| 0 | 2021-07-29 | 0.03764% | 0.09386% | 80.88% | 80.26%
| 0 | 2021-08-05 | 0.3863% | 0.09386% | 81.27% | 80.35%
| 0 | 2021-08-12 | 0.539% | 0.09385% | 81.8% | 80.44%
| 0 | 2021-08-19 | 0.539% | 0.09385% | 82.34% | 80.54%
| 0 | 2021-08-26 | 0.539% | 0.09385% | 82.88% | 80.63%
| 0 | 2021-09-02 | 0.2834% | 0.09385% | 83.17% | 80.73%
| 0 | 2021-09-09 | 0.03764% | 0.09385% | 83.2% | 80.82%
| 0 | 2021-09-16 | 0.006901% | 0.09385% | 83.21% | 80.91%
| 0 | 2021-09-23 | 0% | 0.07821% | 83.21% | 80.99%
| 0 | 2021-09-30 | 0% | 0.09385% | 83.21% | 81.09%
| 0 | 2021-10-07 | 0% | 0.09385% | 83.21% | 81.18% |  |  | 18
| 0 | 2021-10-14 | 0% | 0.09385% | 83.21% | 81.27% |  |  | 126
| 0 | 2021-10-21 | 0% | 0.09385% | 83.21% | 81.37% |  |  | 4453100%
| 0 | 2021-10-28 | 0% | 0.09385% | 83.21% | 81.46% |  |  | 4465700%
| 0 | 2021-11-04 | 0% | 0.09385% | 83.21% | 81.56%
| 0 | 2021-11-11 | 0% | 0.09385% | 83.21% | 81.65%
| 0 | 2021-11-18 | 0% | 0.09385% | 83.21% | 81.74% | [5 empty] | 16.2998
| 0 | 2021-11-25 | 0% | 0.09385% | 83.21% | 81.84% |  | 0.68966 |  |  |  | 4464510%
| 0 | 2021-12-02 | 0.4751% | 0.09385% | 83.69% | 81.93%
| 0 | 2021-12-09 | 1.5% | 0.09385% | 85.19% | 82.02%
| 0 | 2021-12-16 | 1.425% | 0.09385% | 86.61% | 82.12%
| 0 | 2021-12-23 | 0% | 0.09385% | 86.61% | 82.21%
| 0 | 2021-12-30 | 0% | 0.09385% | 86.61% | 82.31%
| 0 | 2022-01-06 | 0% | 0.09385% | 86.61% | 82.4%
| 0 | 2022-01-13 | 0% | 0.09385% | 86.61% | 82.49%
| 0 | 2022-01-20 | 0% | 0.09385% | 86.61% | 82.59%
| 0 | 2022-01-27 | 0% | 0.09385% | 86.61% | 82.68%
| 0 | 2022-02-03 | 0% | 0.09385% | 86.61% | 82.78%
| 0 | 2022-02-10 | 0% | 0.09385% | 86.61% | 82.87%
| 0 | 2022-02-17 | 0% | 0.09385% | 86.61% | 82.96%
| 0 | 2022-02-24 | 0% | 0.09385% | 86.61% | 83.06%
| 0 | 2022-03-03 | 0.5536% | 0.09397% | 87.16% | 83.15%
| 0 | 2022-03-10 | 0.7072% | 0.09385% | 87.87% | 83.24%
| 0 | 2022-03-17 | 1.847% | 0.338% | 89.72% | 83.58%
| 0 | 2022-03-24 | 2.088% | 0.4677% | 91.81% | 84.05%
| 0 | 2022-03-31 | 1.567% | 0.4677% | 93.37% | 84.52%
| 0 | 2022-04-07 | 1.092% | 0.3861% | 94.47% | 84.9%
|  | 2022-04-14 | 0.9063% | 0.3835% | 95.37% | 85.29%
|  | 2022-04-21 | 0.7811% | 0.3668% | 96.15% | 85.65%
|  | 2022-04-28 | 0.8445% | 0.6619% | 97% | 86.32%
|  | 2022-05-05 | 0.4433% | 0.5128% | 97.44% | 86.83%
|  | 2022-05-12 | 1.191% | 0.9916% | 98.63% | 87.42%
|  | 2022-05-19 | 1.086% |  | 99.72%
|  | 2022-05-26 | 0.1968% |  | 99.91%
|  |  | 0.08531% |  | 100%
[157 empty] | 0.26384 | 0.20442
[157 empty] | 34.4071 | 34.6115
Activity ID | Resource ID Name | Activity Name | Start | Finish | Price / Unit | Budgeted Units | sar UNIT | Spreadsheet Field | 2019-06-21 | 2019-06-28 | 2019-07-05 | 2019-07-12 | 43665 | 43672 | 43679 | 2019-08-09 | 2019-08-16 | 43700 | 43707 | 43714 | 43721 | 43728 | 43735 | 43742 | 43749 | 43756 | 43763 | 43770 | 43777 | 43784 | 43791 | 43798 | 43805 | 43812 | 43819 | 43826 | 43833 | 43840 | 43847 | 43854 | 43861 | 43868 | 43875 | 43882 | 43889 | 43896 | 43903 | 43910 | 43917 | 43924 | 43931 | 43938 | 43945 | 43952 | 43959 | 43966 | 43973 | 43980 | 43987 | 43994 | 44001 | 44008 | 44015 | 44022 | 44029 | 44036 | 44043 | 44050 | 44057 | 44064 | 44071 | 44078 | 44085 | 44092 | 44099 | 44106 | 44113 | 44120 | 44127 | 44134 | 44141 | 44148 | 44155 | 44162 | 44169 | 44176 | 44183 | 44190 | 44197 | 44204 | 44211 | 44218 | 44225 | 44232 | 44239 | 44246 | 44253 | 44260 | 44267 | 44274 | 44281 | 44288 | 44295 | 44302 | 44309 | 44316 | 44323 | 44330 | 44337 | 44344 | 44351 | 44358 | 44365 | 44372 | 44379 | 44386 | 44393 | 44400 | 44407 | 44414 | 44421 | 44428 | 44435 | 44442 | 44449 | 44456 | 44463 | 44470 | 44477 | 44484 | 44491 | 44498 | 44505 | 44512 | 44519 | 44526 | 44533 | 44540 | 44547 | 44554 | 44561 | 44568 | 44575 | 44582 | 44589 | 44596 | 44603 | 44610 | 44617 | 44624 | 44631 | 44638 | 44645 | 44652 | 44659 | 44666 | 44673 | 44680 | 44687 | 44694 | 44701 | 44708 | 44715 | 44722 | 44729 | 44736 | 44743 | 44750 | 44757 | 44764 | 44771 | 2022-08-05
Project: AM-BL-UP TB1100101 EW P1-BL-PO- UP- 20220505 |  |  | 23-Jun-19 A | 2022-08-08 |  | --- | 0 | Actual Cost | 24544.76 | 30065.64 | 30017.19 | 2024-04-01 04:34 | 62188.02 | 71188.99 | 51847.19 | 927026% | 7429947% | 100216.24 | 238603.03 | 303112.34 | 320390.26 | 173682.72 | 118981.16 | 119179.7 | 119550.84 | 119552.41 | 119548.25 | 119545.27 | 119611.38 | 119910.82 | 119989.79 | 117710.43 | 100015.87 | 100070.99 | 95699.04 | 93454.97 | 93506.33 | 107499.63 | 144822.55 | 137501.82 | 101128.57 | 157078.13 | 378732.06 | 543861.91 | 379597.27 | 185376.6 | 106643.04 | 106366.18 | 106333.94 | 172972.09 | 223840.91 | 163882.45 | 100483.06 | 405678.47 | 788440.42 | 595257 | 296938.57 | 636292.06 | 636286.49 | 630771.55 | 605275.67 | 622085.35 | 584809.13 | 577174.14 | 585456.65 | 501351.15 | 301712.91 | 575532.11 | 615237.89 | 659307.94 | 659205.94 | 651086.67 | 670700.33 | 589320.18 | 785781.09 | 786002.45 | 785866.71 | 773354.88 | 711370.37 | 699850.86 | 699454.68 | 727946.69 | 623316.08 | 518197.26 | 518197.26 | 518197.26 | 483794.28 | 462250.25 | 385089.7 | 372891.42 | 392714.35 | 343667.48 | 325812.2 | 132606.55 | 265057.18 | 530592.59 | 37412.87 | 37412.87 | 37412.87 | 37412.87 | 37412.87 | 37412.87 | 37412.73 | 37412.66 | 46928.13 | 175081.18 | 175081.18 | 175081.18 | 175081.18 | 175081.18 | 166517.26 | 46894.77 | 37412.66 | 37412.66 | 37412.66 | 37412.66 | 12470.89 | 37412.66 | 37412.28 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 31175.3 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37410.36 | 37458.36 | 37410.36 | 134752.14 | 186424.47 | 186424.47 | 153901.31 | 152855.36 | 146206.64 | 263835.68 | 204419.46
Project: AM-BL-UP TB1100101 EW P1-BL-PO- UP- 20220505 |  |  | 23-Jun-19 A | 2022-08-08 |  | --- | 0 | Cum Actual Cost | 24544.76 | 54610.41 | 84627.6 | 2255-12-14 18:58 | 192198.8 | 263387.8 | 315234.99 | 32450525% | 39880472% | 499020.95 | 737623.99 | 1040736.33 | 1361126.58 | 1534809.3 | 1653790.46 | 1772970.17 | 1892521 | 2012073.42 | 2131621.66 | 2251166.94 | 2370778.32 | 2490689.14 | 2610678.93 | 2728389.36 | 2828405.23 | 2928476.22 | 3024175.26 | 3117630.23 | 3211136.56 | 3318636.19 | 3463458.74 | 3600960.55 | 3702089.13 | 3859167.26 | 4237899.32 | 4781761.23 | 5161358.5 | 5346735.1 | 5453378.15 | 5559744.32 | 5666078.26 | 5839050.36 | 6062891.27 | 6226773.72 | 6327256.79 | 6732935.25 | 7521375.67 | 8116632.67 | 8413571.25 | 9049863.31 | 9686149.8 | 10316921.35 | 10922197.02 | 11544282.36 | 12129091.49 | 12706265.63 | 13291722.29 | 13793073.44 | 14094786.35 | 14670318.45 | 15285556.34 | 15944864.28 | 16604070.22 | 17255156.89 | 17925857.21 | 18515177.39 | 19300958.49 | 20086960.93 | 20872827.64 | 21646182.52 | 22357552.89 | 23057403.76 | 23756858.43 | 24484805.13 | 25108121.21 | 25626318.47 | 26144515.74 | 26662713 | 27146507.28 | 27608757.53 | 27993847.22 | 28366738.64 | 28759453 | 29103120.48 | 29428932.68 | 29561539.22 | 29826596.4 | 30357189 | 30394601.86 | 30432014.73 | 30469427.59 | 30506840.46 | 30544253.33 | 30581666.19 | 30619078.92 | 30656491.59 | 30703419.71 | 30878500.89 | 31053582.07 | 31228663.25 | 31403744.44 | 31578825.62 | 31745342.88 | 31792237.65 | 31829650.31 | 31867062.98 | 31904475.64 | 31941888.31 | 31954359.19 | 31991771.86 | 32029184.14 | 32066594.5 | 32104004.87 | 32141415.23 | 32178825.6 | 32216235.96 | 32253646.32 | 32284821.63 | 32322231.99 | 32359642.36 | 32397052.72 | 32434463.08 | 32471873.45 | 32509283.81 | 32546694.18 | 32584104.54 | 32621514.91 | 32658925.27 | 32696335.64 | 32733746 | 32771156.36 | 32808566.73 | 32845977.09 | 32883387.46 | 32920797.82 | 32958208.19 | 32995618.55 | 33033028.91 | 33070439.28 | 33107849.64 | 33145308.01 | 33182718.37 | 33317470.51 | 33503894.97 | 33690319.44 | 33844220.75 | 33997076.11 | 34143282.75 | 34407118.43 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89
[5 empty] | 39861779 |  |  |  | 0.06157% | 0.07542% | 0.0753% | 0.1139% | 0.156% | 0.1786% | 0.1301% | 0.02326% | 0.1864% | 0.2514% | 0.5986% | 0.7604% | 0.8038% | 0.4357% | 0.2985% | 0.299% | 0.2999% | 0.2999% | 0.2999% | 0.2999% | 0.3001% | 0.3008% | 0.301% | 0.2953% | 0.2509% | 0.251% | 0.2401% | 0.2344% | 0.2346% | 0.2697% | 0.3633% | 0.3449% | 0.2537% | 0.3941% | 0.9501% | 1.364% | 0.9523% | 0.465% | 0.2675% | 0.2668% | 0.2668% | 0.4339% | 0.5615% | 0.4111% | 0.2521% | 1.018% | 1.978% | 1.493% | 0.7449% | 1.596% | 1.596% | 1.582% | 1.518% | 1.561% | 1.467% | 1.448% | 1.469% | 1.258% | 0.7569% | 1.444% | 1.543% | 1.654% | 1.654% | 1.633% | 1.683% | 1.478% | 1.971% | 1.972% | 1.971% | 1.94% | 1.785% | 1.756% | 1.755% | 1.826% | 1.564% | 1.3% | 1.3% | 1.3% | 1.214% | 1.16% | 0.9661% | 0.9355% | 0.9852% | 0.8621% | 0.8174% | 0.3327% | 0.6649% | 1.331% | 0.09386% | 0.09386% | 0.09386% | 0.09386% | 0.09386% | 0.09386% | 0.09386% | 0.09386% | 0.1177% | 0.4392% | 0.4392% | 0.4392% | 0.4392% | 0.4392% | 0.4177% | 0.1176% | 0.09386% | 0.09386% | 0.09386% | 0.09386% | 0.03129% | 0.09386% | 0.09386% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.07821% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09385% | 0.09397% | 0.09385% | 0.338% | 0.4677% | 0.4677% | 0.3861% | 0.3835% | 0.3668% | 0.6619% | 0.5128%
[9 empty] | 0.06157% | 0.137% | 0.2123% | 0.3262% | 0.4822% | 0.6608% | 0.7908% | 0.8141% | 1% | 1.252% | 1.85% | 2.611% | 3.415% | 3.85% | 4.149% | 4.448% | 4.748% | 5.048% | 5.348% | 5.647% | 5.947% | 6.248% | 6.549% | 6.845% | 7.096% | 7.347% | 7.587% | 7.821% | 8.056% | 8.325% | 8.689% | 9.034% | 9.287% | 9.681% | 10.63% | 12% | 12.95% | 13.41% | 13.68% | 13.95% | 14.21% | 14.65% | 15.21% | 15.62% | 15.87% | 16.89% | 18.87% | 20.36% | 21.11% | 22.7% | 24.3% | 25.88% | 27.4% | 28.96% | 30.43% | 31.88% | 33.34% | 34.6% | 35.36% | 36.8% | 38.35% | 40% | 41.65% | 43.29% | 44.97% | 46.45% | 48.42% | 50.39% | 52.36% | 54.3% | 56.09% | 57.84% | 59.6% | 61.42% | 62.99% | 64.29% | 65.59% | 66.89% | 68.1% | 69.26% | 70.23% | 71.16% | 72.15% | 73.01% | 73.83% | 74.16% | 74.83% | 76.16% | 76.25% | 76.34% | 76.44% | 76.53% | 76.63% | 76.72% | 76.81% | 76.91% | 77.02% | 77.46% | 77.9% | 78.34% | 78.78% | 79.22% | 79.64% | 79.76% | 79.85% | 79.94% | 80.04% | 80.13% | 80.16% | 80.26% | 80.35% | 80.44% | 80.54% | 80.63% | 80.73% | 80.82% | 80.91% | 80.99% | 81.09% | 81.18% | 81.27% | 81.37% | 81.46% | 81.56% | 81.65% | 81.74% | 81.84% | 81.93% | 82.02% | 82.12% | 82.21% | 82.31% | 82.4% | 82.49% | 82.59% | 82.68% | 82.78% | 82.87% | 82.96% | 83.06% | 83.15% | 83.24% | 83.58% | 84.05% | 84.52% | 84.9% | 85.29% | 85.65% | 86.32% | 86.83%
Activity ID | Activity Name | Start | Finish | Original Duration | Total Float | Budgeted Total Cost | Spreadsheet Field | time axis 2019-06-23 to 2022-08-14
TB1100101 EW P1-BL-PO- UP- 20220512 |  | 23-Jun-19 A | 2022-08-15 | 1902-08-05 | 0 | 39861779 | Actual Total Cost | 29417.78 | 29918.18 | 32188.72 | 47953.08 | 64627.76 | 68796.72 | 41366.3 | 18767.6 | 81315.37 | 98235.09 | 275805.82 | 300457.77 | 327653.23 | 136290.33 | 118851.99 | 119122.71 | 119409.31 | 119410.37 | 119405.02 | 119403.23 | 119485.91 | 119909.63 | 119747.75 | 114256.13 | 99874.37 | 99964.67 | 94424.04 | 93321.96 | 93364.5 | 115898.37 | 144591.16 | 129988.83 | 100871.54 | 203763.07 | 376606.17 | 543576.96 | 381591.95 | 138873.64 | 106420.71 | 106092.56 | 106106.58 | 194948.16 | 220055.23 | 144144.23 | 102107.85 | 492202.73 | 818476.76 | 544309.42 | 318029.37 | 636061.57 | 636049.92 | 625011.24 | 608158.65 | 622195.85 | 576761.21 | 576886.28 | 589656.16 | 400666.58 | 399628.48 | 571817.65 | 626935.21 | 663130.64 | 656866.34 | 650944.29 | 675282.83 | 606707.56 | 785653.66 | 785705.75 | 785593.28 | 760741.67 | 709554.49 | 699217.88 | 703565.02 | 728203.43 | 588045 | 517965.78 | 517965.78 | 517965.78 | 476682.2 | 447355.34 | 381014.81 | 381220.8 | 380221.16 | 343433.92 | 319633.13 | 87282.31 | 599855.36 | 195331.46 | 37181.39 | 37181.39 | 37181.39 | 37181.39 | 37181.39 | 37181.39 | 37181.22 | 37181.19 | 69641.4 | 174849.7 | 174849.7 | 174849.7 | 174849.7 | 174849.7 | 152823.14 | 37181.19 | 37181.19 | 37181.19 | 37181.19 | 37181.19 | 12393.73 | 37181.19 | 37180.42 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 30982.4 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37178.89 | 37194.89 | 37210.89 | 37178.89 | 166826.02 | 197397.51 | 187560.6 | 158575.54 | 156074.13 | 133300.64 | 176515.29 | 117073.79 | 395257.22
TB1100101 EW P1-BL-PO- UP- 20220512 |  | 23-Jun-19 A | 2022-08-15 | 1902-08-05 | 0 | 39861779 | Cum Actual Total Cost | 29417.78 | 59335.96 | 91524.68 | 139477.76 | 204105.52 | 272902.24 | 314268.54 | 333036.13 | 414351.51 | 512586.6 | 788392.42 | 1088850.19 | 1416503.42 | 1552793.75 | 1671645.74 | 1790768.45 | 1910177.76 | 2029588.14 | 2148993.15 | 2268396.38 | 2387882.29 | 2507791.92 | 2627539.66 | 2741795.8 | 2841670.17 | 2941634.84 | 3036058.87 | 3129380.83 | 3222745.33 | 3338643.7 | 3483234.87 | 3613223.69 | 3714095.23 | 3917858.3 | 4294464.47 | 4838041.43 | 5219633.38 | 5358507.02 | 5464927.73 | 5571020.29 | 5677126.88 | 5872075.04 | 6092130.27 | 6236274.49 | 6338382.34 | 6830585.07 | 7649061.84 | 8193371.25 | 8511400.63 | 9147462.2 | 9783512.12 | 10408523.36 | 11016682.01 | 11638877.86 | 12215639.07 | 12792525.35 | 13382181.51 | 13782848.09 | 14182476.57 | 14754294.23 | 15381229.44 | 16044360.07 | 16701226.41 | 17352170.7 | 18027453.52 | 18634161.09 | 19419814.75 | 20205520.5 | 20991113.78 | 21751855.45 | 22461409.95 | 23160627.83 | 23864192.85 | 24592396.28 | 25180441.28 | 25698407.06 | 26216372.85 | 26734338.63 | 27211020.83 | 27658376.18 | 28039390.99 | 28420611.78 | 28800832.94 | 29144266.86 | 29463899.99 | 29551182.29 | 30151037.66 | 30346369.11 | 30383550.5 | 30420731.89 | 30457913.27 | 30495094.66 | 30532276.05 | 30569457.43 | 30606638.65 | 30643819.84 | 30713461.24 | 30888310.94 | 31063160.64 | 31238010.35 | 31412860.05 | 31587709.75 | 31740532.89 | 31777714.07 | 31814895.26 | 31852076.44 | 31889257.63 | 31926438.82 | 31938832.54 | 31976013.73 | 32013194.15 | 32050373.03 | 32087551.92 | 32124730.81 | 32161909.69 | 32199088.58 | 32236267.46 | 32267249.87 | 32304428.75 | 32341607.64 | 32378786.52 | 32415965.41 | 32453144.3 | 32490323.18 | 32527502.07 | 32564680.95 | 32601859.84 | 32639038.73 | 32676217.61 | 32713396.5 | 32750575.38 | 32787754.27 | 32824933.15 | 32862112.04 | 32899290.93 | 32936469.81 | 32973648.7 | 33010827.58 | 33048006.47 | 33085201.35 | 33122412.24 | 33159591.13 | 33326417.15 | 33523814.66 | 33711375.27 | 33869950.81 | 34026024.94 | 34159325.58 | 34335840.87 | 34452914.66 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88 | 34848171.88
0.2937%
86.43%
Formulas:
Weekly Average Actual Last 2 Months = AVERAGEIFS(Table25[Weekly Actual],Table25[Date],"<="&I2,Table25[Date],">="&WORKDAY.INTL(I2,-40,7))
Weekly Average Plan Next 2 Months = AVERAGEIFS(Table25[Weekly Plan],Table25[Date],">="&I2,Table25[Date],"<="&WORKDAY.INTL(I2,40,7))
Date = IFERROR(IF(WORKDAY.INTL([Date, row above],4,7)>Timeline[Forecast End Date],"",WORKDAY.INTL([Date, row above],4,7)),"")

## Variance Analysis
Report Week Date
2022-05-12
| Date | Construction Planned % | Construction Actual % | Procurement Planned % | Procurement Actual % | Engineering Planned % | Engineering Actual % | Prelims Planned % | Prelims Actual %
0 | 2019-06-23 | 0% | 0% | 6% |  | 0.8677% |  | 0.5378% | 0% | 0.5378%
0 | 2019-06-27 | 0.009273% | 0.007639% | 16% |  | 1.404% |  | 0.5378% | 0.3123%
0 | 2019-07-04 | 0.02062% | 0.01703% | 26% |  | 1.404% |  | 1.273% | 0.6948%
0 | 2019-07-11 | 0.0318% | 0.02626% | 36% |  | 1.394% |  | 1.926% | 1.077%
0 | 2019-07-18 | 0.04422% | 0.03648% | 46% |  | 1.38% | 0.7609% | 3.017% | 1.671%
0 | 2019-07-25 | 0.05903% | 0.04911% | 56% |  | 1.38% | 2.14% | 4.319% | 2.491%
0 | 2019-08-01 | 0.1181% | 0.1033% | 66% |  | 1.413% | 3.526% | 5.586% | 3.251%
0 | 2019-08-08 | 0.1779% | 0.1574% | 76% |  | 1.392% | 4.478% | 7.099% | 3.738%
0 | 2019-08-15 | 0.1896% | 0.1679% | 86% | 0.466% | 1.386% | 4.502% | 8.762% | 3.807%
0 | 2019-08-22 | 0.299% | 0.2638% | 96% | 1.864% | 1.788% | 4.575% | 10.43% | 4.337%
0 | 2019-08-29 | 0.4741% | 0.4156% | 100% | 3.256% | 3.649% | 4.648% | 11.84% | 4.98%
0 | 2019-09-05 | 1.191% | 1.003% | 0% | 4.614% | 3.586% | 4.722% | 16.9% | 5.624%
0 | 2019-09-12 | 2.216% | 1.825% | 0% | 6.179% | 3.586% | 4.795% | 24.46% | 6.115%
0 | 2019-09-19 | 3.02% | 2.646% | 0% | 7.847% | 3.586% | 4.868% | 32.02% | 6.844%
0 | 2019-09-26 | 3.141% | 2.979% | 0% | 9.236% | 3.108% | 4.929% | 39.56% | 7.712%
0 | 2019-10-03 | 3.287% | 3.097% | 0% | 10.9% | 2.857% | 5.314% | 47.02% | 8.754%
0 | 2019-10-10 | 3.432% | 3.215% | 0% | 12.57% | 0.893% | 6.133% | 54.17% | 9.801%
0 | 2019-10-17 | 3.577% | 3.333% | 0% | 14.24% | 0.699% | 6.951% | 57.09% | 10.85%
0 | 2019-10-24 | 3.722% | 3.451% | 0% | 15.91% | 1.36% | 7.77% | 61.62% | 11.9%
0 | 2019-10-31 | 3.867% | 3.568% | 0% | 17.57% | 1.947% | 8.588% | 63.63% | 12.95%
0 | 2019-11-07 | 4.012% | 3.686% | 0% | 19.24% | 1.738% | 9.407% | 65.71% | 14.01%
0 | 2019-11-14 | 4.155% | 3.804% | 0% | 20.91% | 1.377% | 11.02% | 67.78% | 15.06%
0 | 2019-11-21 | 4.197% | 3.922% | 0% | 22.58% | 6.696% | 16.69% | 69.86% | 16.11%
0 | 2019-11-28 | 4.238% | 4.04% | 0% | 24.25% | 5.735% | 20.75% | 71.93% | 17.16%
0 | 2019-12-05 | 4.28% | 4.144% | 0% | 25.91% | 4.704% | 24.82% | 74.01% | 18.24%
0 | 2019-12-12 | 4.318% | 4.178% | 0% | 27.58% | 4.401% | 28.89% | 76.08% | 19.39%
0 | 2019-12-19 | 4.348% | 4.212% | 0% | 29.25% | 0.9135% | 33.83% | 77.92% | 20.54%
0 | 2019-12-26 | 4.379% | 4.246% | 0% | 30.92% | 3.221% | 39.97% | 78.73% | 21.62%
0 | 2020-01-02 | 4.409% | 4.28% | 0% | 32.58% | 5.849% | 46.11% | 79.43% | 22.67%
0 | 2020-01-09 | 4.44% | 4.314% | 0% | 34.25% | 4.524% | 52.26% | 80.27% | 23.72%
0 | 2020-01-16 | 4.521% | 4.393% | 0% | 35.92% | 4.266% | 58.4% | 81.11% | 24.78%
0 | 2020-01-23 | 4.758% | 4.588% | 0% | 37.59% | 4.175% | 64.54% | 81.95% | 25.83%
0 | 2020-01-30 | 4.924% | 4.761% | 0% | 39.26% | 6.428% | 70.68% | 82.79% | 26.88%
0 | 2020-02-06 | 4.997% | 4.819% | 0% | 40.93% | 3.181% | 76.98% | 83.64% | 27.93%
0 | 2020-02-13 | 5.228% | 5.014% | 0% | 42.59% | 2.651% | 83.3% | 84.48% | 29.16%
0 | 2020-02-20 | 6.345% | 5.892% | 0% | 44.26% | 1.06% | 89.62% | 85.25% | 30.44%
0 | 2020-02-27 | 7.902% | 7.314% | 0% | 45.93% | 0% | 89.97% | 86.09% | 31.62%
0 | 2020-03-05 | 8.633% | 8.193% | 0% | 47.6% | 0% | 90.6% | 86.93% | 32.93%
0 | 2020-03-12 | 8.729% | 8.391% | 0% | 49.26% | 0% | 91.55% | 87.77% | 34.55%
0 | 2020-03-19 | 8.808% | 8.446% | 0% | 50.93% | 0% | 94.76% | 88.61% | 35.7%
0 | 2020-03-26 | 8.869% | 8.5% | 0% | 52.6% | 0% | 94.78% | 89.45% | 36.85%
0 | 2020-04-02 | 8.918% | 8.555% | 0% | 54.27% | 0% | 94.78% | 90.3% | 38%
0 | 2020-04-09 | 9.734% | 8.82% | 0% | 55.93% | 0% | 94.78% | 91.14% | 39.15%
0 | 2020-04-16 | 9.788% | 9.299% | 0% | 57.6% | 0% | 94.78% | 91.98% | 40.05%
0 | 2020-04-23 | 9.836% | 9.601% | 0% | 59.21% | 0% | 94.78% | 92.82% | 40.9%
0 | 2020-04-30 | 9.875% | 9.747% | 0% | 60.54% | 0% | 94.78% | 93.66% | 41.58%
0 | 2020-05-07 | 11.84% | 10.85% | 0% | 61.86% | 0% | 96.38% | 94.5% | 42.26%
0 | 2020-05-14 | 16.3% | 13.16% | 0% | 63.18% | 0% | 97.04% | 95.34% | 42.94%
0 | 2020-05-21 | 20.64% | 14.86% | 0% | 64.5% | 0% | 97.04% | 96.18% | 43.62%
0 | 2020-05-28 | 22.85% | 15.69% | 0% | 65.33% | 0% | 97.04% | 97.03% | 44.02%
0 | 2020-06-04 | 26.64% | 17.48% | 0% | 66.98% | 0% | 97.04% | 97.87% | 44.87%
0 | 2020-06-11 | 30.37% | 19.27% | 0% | 68.63% | 0% | 97.04% | 98.71% | 45.72%
0 | 2020-06-18 | 34.09% | 21.05% | 0% | 70.28% | 0% | 97.04% | 99.55% | 46.49%
0 | 2020-06-25 | 37.82% | 22.84% | 0% | 71.93% | 0% | 97.04% | 100% | 46.9%
0 | 2020-07-02 | 41.42% | 24.63% | 0% | 73.58% | 0% | 97.04% | 0% | 47.54%
0 | 2020-07-09 | 44.99% | 26.3% | 0% | 75.23% | 0% | 97.04% | 0% | 48.18%
0 | 2020-07-16 | 46.83% | 27.95% | 0% | 76.88% | 0% | 97.04% | 0% | 48.82%
0 | 2020-07-23 | 48.26% | 29.63% | 0% | 78.53% | 0% | 97.04% | 0% | 49.46%
0 | 2020-07-30 | 49.49% | 31.06% | 0% | 79.64% | 0% | 97.61% | 0% | 49.99%
0 | 2020-08-06 | 50.25% | 31.93% | 0% | 80.74% | 0% | 98.18% | 0% | 50.31%
0 | 2020-08-13 | 51.68% | 33.57% | 0% | 82.39% | 0% | 98.2% | 0% | 50.95%
0 | 2020-08-20 | 53.28% | 35.34% | 0% | 84.04% | 0% | 98.22% | 0% | 51.59%
0 | 2020-08-27 | 55.42% | 37.25% | 0% | 85.69% | 0% | 98.25% | 0% | 52.23%
0 | 2020-09-03 | 57.67% | 39.17% | 0% | 87.34% | 0% | 98.27% | 0% | 52.81%
0 | 2020-09-10 | 59.79% | 41.09% | 0% | 88.99% | 0% | 98.29% | 0% | 53.27%
0 | 2020-09-17 | 61.49% | 43.07% | 0% | 90.64% | 0% | 98.31% | 0% | 53.73%
0 | 2020-09-24 | 63.55% | 44.83% | 0% | 92.02% | 0% | 98.33% | 0% | 54.06%
0 | 2020-10-01 | 67.26% | 47.19% | 0% | 93.67% | 0% | 98.35% | 0% | 54.45%
0 | 2020-10-08 | 68.94% | 49.55% | 0% | 95.32% | 0% | 98.37% | 0% | 54.83%
0 | 2020-10-15 | 70.41% | 51.91% | 0% | 96.97% | 0% | 98.4% | 0% | 55.21%
0 | 2020-10-22 | 71.68% | 54.23% | 0% | 98.62% | 0% | 98.42% | 0% | 55.59%
0 | 2020-10-29 | 72.01% | 56.36% | 0% | 100% | 0% | 98.44% | 0% | 55.98%
0 | 2020-11-05 | 72.06% | 58.47% | 0% |  | 0% | 98.46% | 0% | 56.36%
0 | 2020-11-12 | 72.11% | 60.59% | 0% |  | 0% | 98.49% | 0% | 56.74%
0 | 2020-11-19 | 72.27% | 62.79% | 0% |  | 0% | 98.51% | 0% | 57.12%
0 | 2020-11-26 | 72.43% | 64.66% | 0% |  | 0% | 98.53% | 0% | 57.51%
0 | 2020-12-03 | 72.59% | 66.21% | 0% |  | 0% | 98.55% | 0% | 57.89%
0 | 2020-12-10 | 72.76% | 67.75% | 0% |  | 0% | 98.57% | 0% | 58.27%
0 | 2020-12-17 | 72.92% | 69.3% | 0% |  | 0% | 98.6% | 0% | 58.65%
0 | 2020-12-24 | 73.08% | 70.73% | 0% |  | 0% | 98.62% | 0% | 59.04%
0 | 2020-12-31 | 73.22% | 72.1% | 0% |  | 0% | 98.64% | 0% | 59.42%
0 | 2021-01-07 | 73.27% | 73.22% | 0% |  | 0% | 98.66% | 0% | 59.8%
0 | 2021-01-14 | 73.32% | 74.31% | 0% |  | 0% | 98.68% | 0% | 60.18%
0 | 2021-01-21 | 73.36% | 75.46% | 0% |  | 0% | 98.71% | 0% | 60.56%
0 | 2021-01-28 | 73.41% | 76.45% | 0% |  | 0% | 98.73% | 0% | 60.95%
0 | 2021-02-04 | 73.46% | 77.39% | 0% |  | 0% | 98.75% | 0% | 61.33%
0 | 2021-02-11 | 73.5% | 77.73% | 0% |  | 0% | 98.77% | 0% | 61.71%
0 | 2021-02-18 | 73.55% | 78.47% | 0% |  | 0% | 99.49% | 0% | 62.09%
0 | 2021-02-25 | 73.6% | 80.06% | 0% |  | 0% | 99.51% | 0% | 62.48%
0 | 2021-03-04 | 73.65% | 80.09% | 0% |  | 0% | 99.53% | 0% | 62.86%
0 | 2021-03-11 | 73.69% | 80.12% | 0% | 0% | 0% | 99.56% | 0% | 63.24%
0 | 2021-03-18 | 73.74% | 80.15% | 0% | 0% | 0% | 99.58% | 0% | 63.62%
0 | 2021-03-25 | 73.79% | 80.19% | 0% | 0% | 0% | 99.6% | 0% | 64.01%
0 | 2021-04-01 | 73.84% | 80.22% | 0% | 0% | 0% | 99.62% | 100% | 64.39%
0 | 2021-04-08 | 73.88% | 80.25% | 0% | 0% | 100% | 99.65% | 100% | 64.77%
0 | 2021-04-15 | 73.93% | 80.28% |  |  |  | 99.67% |  | 65.15%
0 | 2021-04-22 | 73.98% | 80.32% |  |  |  | 99.69% |  | 65.54%
0 | 2021-04-29 | 74.22% | 80.38% |  |  |  | 99.71% |  | 65.92%
0 | 2021-05-06 | 75.37% | 80.84% |  |  |  | 99.73% |  | 66.3%
0 | 2021-05-13 | 76.66% | 81.31% |  |  |  | 99.76% |  | 66.68%
0 | 2021-05-20 | 77.18% | 81.77% |  |  |  | 99.78% |  | 67.07%
0 | 2021-05-27 | 77.23% | 82.24% |  |  |  | 99.8% |  | 67.45%
0 | 2021-06-03 | 77.28% | 82.7% |  |  |  | 99.82% |  | 67.83%
0 | 2021-06-10 | 77.32% | 83.14% |  |  |  | 99.84% |  | 68.21%
0 | 2021-06-17 | 77.37% | 83.2% |  |  |  | 99.87% |  | 68.6%
0 | 2021-06-24 | 77.42% | 83.24% |  |  |  | 99.89% |  | 68.98%
0 | 2021-07-01 | 77.47% | 83.27% |  |  |  | 99.91% |  | 69.36%
0 | 2021-07-08 | 77.51% | 83.3% |  |  |  | 99.93% |  | 69.74%
0 | 2021-07-15 | 77.56% | 83.33% |  |  |  | 99.96% |  | 70.13%
0 | 2021-07-22 | 77.58% | 83.34% |  |  |  | 99.96% |  | 70.25%
0 | 2021-07-29 | 77.62% | 83.38% |  |  |  | 99.99% |  | 70.64%
0 | 2021-08-05 | 78.11% | 83.41% |  |  |  | 100% |  | 71.02%
0 | 2021-08-12 | 78.78% | 83.44% | [5 empty] | 71.4%
0 | 2021-08-19 | 79.46% | 83.47% | [5 empty] | 71.78%
0 | 2021-08-26 | 80.13% | 83.51% | [5 empty] | 72.17%
0 | 2021-09-02 | 80.49% | 83.54% | [5 empty] | 72.55%
0 | 2021-09-09 | 80.53% | 83.57% | [5 empty] | 72.93%
0 | 2021-09-16 | 80.54% | 83.6% | [5 empty] | 73.31%
0 | 2021-09-23 | 80.54% | 83.63% | [5 empty] | 73.63%
0 | 2021-09-30 | 80.54% | 83.66% | [5 empty] | 74.01%
0 | 2021-10-07 | 80.54% | 83.7% | [5 empty] | 74.4%
0 | 2021-10-14 | 80.54% | 83.73% | [5 empty] | 74.78%
0 | 2021-10-21 | 80.54% | 83.76% | [5 empty] | 75.16%
0 | 2021-10-28 | 80.54% | 83.79% | 100% | 100% | 100% | 100% | 100% | 75.54%
0 | 2021-11-04 | 80.54% | 83.83% | 100% | 100% | 100% | 100% | 100% | 75.93%
0 | 2021-11-11 | 80.54% | 83.86% | 100% | 100% | 100% | 100% | 100% | 76.31%
0 | 2021-11-18 | 80.54% | 83.89% | 100% | 100% | 100% | 100% | 100% | 76.69%
0 | 2021-11-25 | 80.54% | 83.92% | 100% | 100% | 100% | 100% | 100% | 77.07%
0 | 2021-12-02 | 81.14% | 83.96% | 100% | 100% | 100% | 100% | 100% | 77.46%
0 | 2021-12-09 | 83.02% | 83.99% | 100% | 100% | 100% | 100% | 100% | 77.84%
0 | 2021-12-16 | 84.8% | 84.02% | 100% | 100% | 100% | 100% | 100% | 78.22%
0 | 2021-12-23 | 84.8% | 84.05% | 100% | 100% | 100% | 100% | 100% | 78.6%
0 | 2021-12-30 | 84.8% | 84.09% | 100% | 100% | 100% | 100% | 100% | 78.99%
0 | 2022-01-06 | 84.8% | 84.12% | 100% | 100% | 100% | 100% | 100% | 79.37%
0 | 2022-01-13 | 84.8% | 84.15% | 100% | 100% | 100% | 100% | 100% | 79.75%
0 | 2022-01-20 | 84.8% | 84.18% | 100% | 100% | 100% | 100% | 100% | 80.13%
0 | 2022-01-27 | 84.8% | 84.22% | 100% | 100% | 100% | 100% | 100% | 80.52%
0 | 2022-02-03 | 84.8% | 84.25% | 100% | 100% | 100% | 100% | 100% | 80.9%
0 | 2022-02-10 | 84.8% | 84.28% | [5 empty] | 81.28%
0 | 2022-02-17 | 84.8% | 84.31% | [5 empty] | 81.66%
0 | 2022-02-24 | 84.8% | 84.35% | [5 empty] | 82.05%
0 | 2022-03-03 | 85.38% | 84.38% |  |  |  |  | 88.16% | 82.43%
0 | 2022-03-10 | 86.15% | 84.41% |  |  |  |  | 89.44% | 82.81% |  |  |  | 72876
0 | 2022-03-17 | 88.35% | 84.75% |  |  |  |  | 90.72% | 83.19% |  |  |  |  | 89.33%
0 | 2022-03-24 | 90.85% | 85.25% |  |  |  |  | 92% | 83.58% |  |  |  | 81578.19
0 | 2022-03-31 | 92.7% | 85.75% |  |  |  |  | 93.28% | 83.96%
0 | 2022-04-07 | 93.95% | 86.18% |  |  |  |  | 94.56% | 84.22%
0 | 2022-04-14 | 94.97% | 86.61% |  |  |  |  | 95.43% | 84.45%
0 | 2022-04-21 | 95.83% | 87.01% |  |  |  |  | 96.2% | 84.68%
0 | 2022-04-28 | 96.77% | 87.79% |  |  |  |  | 96.97% | 84.91%
0 | 2022-05-05 | 97.21% | 88.43% |  |  |  |  | 97.74% | 84.94%
Current | 2022-05-12 | 98.59% | 89.15% |  |  |  |  | 98.08% | 85.04%
0 | 2022-05-19 | 99.83% | [5 empty] | 99.36%
0 | 2022-05-26 | 99.96% | [5 empty] | 100%
0 |  | 100%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Activity ID | Activity Name | Schedule % Complete | Performance % Complete | Cost % Complete | Total Float | Actual Total Cost | Earned Value Cost | Planned Value Labor Units | Earned Value Labor Units | Start | Finish | BL Project Start | BL Project Finish | BL Project Duration | Budgeted Total Cost | Original Duration | BL Project Total Float | Percent Complete Type | Spreadsheet Field | time axis 2019-06-21 to 2022-08-05
|  |  | CUTTING (EXCAVATION) |  | 96.87% | 88.43% | 88.43% | 0 | 28135430.88 | 28135414.09 | 356759 | 352596 | 23-Jun-19 A | 2022-08-08 | 2019-06-23 | 2022-05-31 | 883 | 31817736.01 | 942 |  |  | Actual Total Cost | 2430.5 | 2986.95 | 2938.5 | 3250.68 | 4018.43 | 17236.59 | 17228.82 | 3324.9 | 30508.97 | 48306.7 | 186871.51 | 261507.61 | 261285.28 | 105915.74 | 37641.29 | 37455.95 | 37501.01 | 37502.59 | 37498.43 | 37495.45 | 37495.45 | 37498.13 | 37503.19 | 33057.84 | 10831.11 | 10831.11 | 10831.11 | 10853.03 | 10904.39 | 24892.8 | 62213.08 | 54893.36 | 18514.75 | 62029.43 | 279394.86 | 452571.62 | 279564.11 | 62992.45 | 17441.57 | 17442.49 | 17455.22 | 84093.38 | 152574.36 | 96119.83 | 46338.29 | 351444.24 | 734167.12 | 541120.48 | 265358.94 | 568621.41 | 568615.84 | 568623.5 | 568632.7 | 569357.86 | 532081.64 | 524446.65 | 532729.17 | 457352.94 | 275290.53 | 522802.32 | 562508.1 | 606578.15 | 610692.03 | 611004.53 | 630618.19 | 559614.94 | 751243.76 | 751465.12 | 751329.38 | 738817.55 | 676833.05 | 672769.87 | 672373.69 | 700865.71 | 596235.1 | 491116.27 | 491116.27 | 491116.27 | 456713.29 | 435169.26 | 358008.71 | 345810.43 | 365633.36 | 316586.5 | 298731.21 | 105525.56 | 237920.19 | 503495.61 | 10331.88 | 10331.88 | 10331.88 | 10331.88 | 10331.88 | 10331.88 | 10331.74 | 10331.67 | 19847.14 | 148000.19 | 148000.19 | 148000.19 | 148000.19 | 148000.19 | 139436.27 | 19813.78 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 3443.89 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 8609.73 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10331.67 | 10379.67 | 10331.67 | 107673.45 | 159345.78 | 159345.78 | 135623.2 | 136608.15 | 129959.42 | 247588.47 | 201711.59
|  |  | CUTTING (EXCAVATION) |  | 96.87% | 88.43% | 88.43% | 0 | 28135430.88 | 28135414.09 | 356759 | 352596 | 23-Jun-19 A | 2022-08-08 | 2019-06-23 | 44712 | 883 | 31817736.01 | 94200% |  |  | Cum Actual Total Cost | 2430.5 | 5417.46 | 8355.96 | 11606.63 | 15625.07 | 32861.65 | 50090.48 | 53415.38 | 83924.34 | 132231.05 | 319102.56 | 580610.16 | 841895.44 | 947811.19 | 985452.48 | 1022908.43 | 1060409.44 | 1097912.04 | 1135410.46 | 1172905.91 | 1210401.36 | 1247899.5 | 1285402.68 | 1318460.53 | 1329291.64 | 1340122.75 | 1350953.86 | 1361806.88 | 1372711.27 | 1397604.07 | 1459817.14 | 1514710.5 | 1533225.26 | 1595254.68 | 1874649.54 | 2327221.16 | 2606785.28 | 2669777.73 | 2687219.3 | 2704661.79 | 2722117.01 | 2806210.39 | 2958784.75 | 3054904.59 | 3101242.88 | 3452687.12 | 4186854.24 | 4727974.72 | 4993333.66 | 5561955.07 | 6130570.91 | 6699194.42 | 7267827.11 | 7837184.97 | 8369266.61 | 8893713.26 | 9426442.43 | 9883795.36 | 10159085.89 | 10681888.21 | 11244396.31 | 11850974.46 | 12461666.49 | 13072671.03 | 13703289.22 | 14262904.15 | 15014147.92 | 15765613.04 | 16516942.42 | 17255759.96 | 17932593.01 | 18605362.88 | 19277736.57 | 19978602.28 | 20574837.37 | 21065953.65 | 21557069.92 | 22048186.19 | 22504899.48 | 22940068.74 | 23298077.45 | 23643887.88 | 24009521.25 | 24326107.74 | 24624838.95 | 24730364.51 | 24968284.7 | 25471780.3 | 25482112.18 | 25492444.06 | 25502775.93 | 25513107.81 | 25523439.69 | 25533771.56 | 25544103.31 | 25554434.98 | 25574282.12 | 25722282.31 | 25870282.5 | 26018282.69 | 26166282.88 | 26314283.08 | 26453719.35 | 26473533.13 | 26483864.81 | 26494196.48 | 26504528.16 | 26514859.83 | 26518303.72 | 26528635.4 | 26538967.07 | 26549298.75 | 26559630.42 | 26569962.1 | 26580293.77 | 26590625.45 | 26600957.12 | 26609566.85 | 26619898.53 | 26630230.2 | 26640561.88 | 26650893.55 | 26661225.23 | 26671556.9 | 26681888.58 | 26692220.25 | 26702551.93 | 26712883.6 | 26723215.28 | 26733546.95 | 26743878.63 | 26754210.3 | 26764541.98 | 26774873.65 | 26785205.33 | 26795537 | 26805868.68 | 26816200.35 | 26826532.03 | 26836863.7 | 26847243.38 | 26857575.05 | 26965248.5 | 27124594.28 | 27283940.05 | 27419563.25 | 27556171.4 | 27686130.82 | 27933719.29 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88 | 28135430.88
[23 empty] | 0.007639% | 0.009388% | 0.009235% | 0.01022% | 0.01263% | 0.05417% | 0.05415% | 0.01045% | 0.09589% | 0.1518% | 0.5873% | 0.8219% | 0.8212% | 0.3329% | 0.1183% | 0.1177% | 0.1179% | 0.1179% | 0.1179% | 0.1178% | 0.1178% | 0.1179% | 0.1179% | 0.1039% | 0.03404% | 0.03404% | 0.03404% | 0.03411% | 0.03427% | 0.07824% | 0.1955% | 0.1725% | 0.05819% | 0.195% | 0.8781% | 1.422% | 0.8786% | 0.198% | 0.05482% | 0.05482% | 0.05486% | 0.2643% | 0.4795% | 0.3021% | 0.1456% | 1.105% | 2.307% | 1.701% | 0.834% | 1.787% | 1.787% | 1.787% | 1.787% | 1.789% | 1.672% | 1.648% | 1.674% | 1.437% | 0.8652% | 1.643% | 1.768% | 1.906% | 1.919% | 1.92% | 1.982% | 1.759% | 2.361% | 2.362% | 2.361% | 2.322% | 2.127% | 2.114% | 2.113% | 2.203% | 1.874% | 1.544% | 1.544% | 1.544% | 1.435% | 1.368% | 1.125% | 1.087% | 1.149% | 0.995% | 0.9389% | 0.3317% | 0.7478% | 1.582% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.06238% | 0.4651% | 0.4651% | 0.4651% | 0.4651% | 0.4651% | 0.4382% | 0.06227% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.01082% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.02706% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03247% | 0.03262% | 0.03247% | 0.3384% | 0.5008% | 0.5008% | 0.4263% | 0.4293% | 0.4084% | 0.7781% | 0.634%
[23 empty] | 0.007639% | 0.01703% | 0.02626% | 0.03648% | 0.04911% | 0.1033% | 0.1574% | 0.1679% | 0.2638% | 0.4156% | 1.003% | 1.825% | 2.646% | 2.979% | 3.097% | 3.215% | 3.333% | 3.451% | 3.568% | 3.686% | 3.804% | 3.922% | 4.04% | 4.144% | 4.178% | 4.212% | 4.246% | 4.28% | 4.314% | 4.393% | 4.588% | 4.761% | 4.819% | 5.014% | 5.892% | 7.314% | 8.193% | 8.391% | 8.446% | 8.5% | 8.555% | 8.82% | 9.299% | 9.601% | 9.747% | 10.85% | 13.16% | 14.86% | 15.69% | 17.48% | 19.27% | 21.05% | 22.84% | 24.63% | 26.3% | 27.95% | 29.63% | 31.06% | 31.93% | 33.57% | 35.34% | 37.25% | 39.17% | 41.09% | 43.07% | 44.83% | 47.19% | 49.55% | 51.91% | 54.23% | 56.36% | 58.47% | 60.59% | 62.79% | 64.66% | 66.21% | 67.75% | 69.3% | 70.73% | 72.1% | 73.22% | 74.31% | 75.46% | 76.45% | 77.39% | 77.73% | 78.47% | 80.06% | 80.09% | 80.12% | 80.15% | 80.19% | 80.22% | 80.25% | 80.28% | 80.32% | 80.38% | 80.84% | 81.31% | 81.77% | 82.24% | 82.7% | 83.14% | 83.2% | 83.24% | 83.27% | 83.3% | 83.33% | 83.34% | 83.38% | 83.41% | 83.44% | 83.47% | 83.51% | 83.54% | 83.57% | 83.6% | 83.63% | 83.66% | 83.7% | 83.73% | 83.76% | 83.79% | 83.83% | 83.86% | 83.89% | 83.92% | 83.96% | 83.99% | 84.02% | 84.05% | 84.09% | 84.12% | 84.15% | 84.18% | 84.22% | 84.25% | 84.28% | 84.31% | 84.35% | 84.38% | 84.41% | 84.75% | 85.25% | 85.75% | 86.18% | 86.61% | 87.01% | 87.79% | 88.43%
31817736.01
|  |  | Activity ID | Activity Name | Schedule % Complete | Performance % Complete | Cost % Complete | Total Float | Actual Total Cost | Earned Value Cost | Planned Value Labor Units | Earned Value Labor Units | Start | Finish | BL Project Start | BL Project Finish | BL Project Duration | Budgeted Total Cost | Original Duration | BL Project Total Float | Percent Complete Type | Spreadsheet Field | time axis 2019-06-21 to 2022-07-08
|  |  | Preliminaries |  | 99.2% | 84.94% | 84.94% | 26 | 6014161.84 | 6013758.34 | 32770800% | 27249900% | 23-Jun-19 A | 2022-07-09 | 2019-06-23 | 2022-05-16 | 87000% | 7080210.57 | 35900% |  |  | Actual Total Cost | 22114.26 | 27078.69 | 27078.69 | 42073.33 | 58035.08 | 53800.1 | 34499.96 | 4891.85 | 37469.42 | 45588.46 | 45588.6 | 34764.17 | 51566.78 | 61485.15 | 73782.18 | 74108.25 | 74434.32 | 74434.32 | 74434.32 | 74434.32 | 74434.32 | 74434.32 | 74434.32 | 76700.31 | 81232.29 | 81232.29 | 76700.31 | 74434.32 | 74434.32 | 74434.32 | 74434.32 | 74434.32 | 74434.32 | 86863.03 | 91151.62 | 83621.32 | 92445.52 | 114774.52 | 81348.91 | 81348.91 | 81348.91 | 81348.91 | 63736.74 | 60214.31 | 48171.45 | 48171.45 | 48171.45 | 48171.45 | 28100.01 | 60214.31 | 60214.31 | 54691.71 | 29186.63 | 45271.15 | 45271.15 | 45271.15 | 45271.15 | 37725.96 | 22635.57 | 45271.15 | 45271.15 | 45271.15 | 41055.27 | 32623.5 | 32623.5 | 23489.71 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 9026.23 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 22565.57 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 27078.69 | 18278.12 | 16247.21 | 16247.21 | 16247.21 | 2707.87
|  |  | Preliminaries |  | 99.2% | 84.94% | 84.94% | 26 | 6014161.84 | 6013758.34 | 32770800% | 27249900% | 23-Jun-19 A | 2022-07-09 | 2019-06-23 | 2022-05-16 | 87000% | 7080210.57 | 35900% |  |  | Cum Actual Total Cost | 22114.26 | 49192.95 | 76271.64 | 118344.97 | 176380.05 | 230180.15 | 264680.12 | 269571.97 | 307041.39 | 352629.84 | 398218.44 | 432982.61 | 484549.39 | 546034.54 | 619816.72 | 693924.96 | 768359.28 | 842793.6 | 917227.92 | 991662.24 | 1066096.56 | 1140530.88 | 1214965.2 | 1291665.51 | 1372897.8 | 1454130.1 | 1530830.41 | 1605264.73 | 1679699.04 | 1754133.36 | 1828567.68 | 1903002 | 1977436.32 | 2064299.36 | 2155450.98 | 2239072.3 | 2331517.81 | 2446292.33 | 2527641.24 | 2608990.15 | 2690339.06 | 2771687.97 | 2835424.72 | 2895639.03 | 2943810.47 | 2991981.92 | 3040153.37 | 3088324.82 | 3116424.83 | 3176639.14 | 3236853.45 | 3291545.16 | 3320731.79 | 3366002.94 | 3411274.09 | 3456545.24 | 3501816.39 | 3539542.34 | 3562177.92 | 3607449.07 | 3652720.22 | 3697991.36 | 3739046.63 | 3771670.13 | 3804293.63 | 3827783.34 | 3854862.02 | 3881940.71 | 3909019.4 | 3936098.09 | 3963176.78 | 3990255.47 | 4017334.16 | 4044412.85 | 4071491.54 | 4098570.23 | 4125648.92 | 4152727.61 | 4179806.3 | 4206884.99 | 4233963.67 | 4261042.36 | 4288121.05 | 4315199.74 | 4342278.43 | 4369357.12 | 4396435.81 | 4423514.5 | 4450593.19 | 4477671.88 | 4504750.57 | 4531829.26 | 4558907.95 | 4585986.64 | 4613065.33 | 4640144.01 | 4667222.7 | 4694301.39 | 4721380.08 | 4748458.77 | 4775537.46 | 4802616.15 | 4829694.84 | 4856773.53 | 4883852.22 | 4910930.91 | 4938009.6 | 4965088.29 | 4974114.52 | 5001193.21 | 5028271.89 | 5055350.58 | 5082429.27 | 5109507.96 | 5136586.65 | 5163665.34 | 5190744.03 | 5213309.6 | 5240388.29 | 5267466.98 | 5294545.67 | 5321624.36 | 5348703.05 | 5375781.74 | 5402860.43 | 5429939.12 | 5457017.81 | 5484096.5 | 5511175.19 | 5538253.88 | 5565332.57 | 5592411.25 | 5619489.94 | 5646568.63 | 5673647.32 | 5700726.01 | 5727804.7 | 5754883.39 | 5781962.08 | 5809040.77 | 5836119.46 | 5863198.15 | 5890276.84 | 5917355.53 | 5944434.22 | 5962712.33 | 5978959.54 | 5995206.76 | 6011453.97 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84 | 6014161.84
[23 empty] | 0.3123% | 0.6948% | 1.077% | 1.671% | 2.491% | 3.251% | 3.738% | 3.807% | 4.337% | 4.98% | 5.624% | 6.115% | 6.844% | 7.712% | 8.754% | 9.801% | 10.85% | 11.9% | 12.95% | 14.01% | 15.06% | 16.11% | 17.16% | 18.24% | 19.39% | 20.54% | 21.62% | 22.67% | 23.72% | 24.78% | 25.83% | 26.88% | 27.93% | 29.16% | 30.44% | 31.62% | 32.93% | 34.55% | 35.7% | 36.85% | 38% | 39.15% | 40.05% | 40.9% | 41.58% | 42.26% | 42.94% | 43.62% | 44.02% | 44.87% | 45.72% | 46.49% | 46.9% | 47.54% | 48.18% | 48.82% | 49.46% | 49.99% | 50.31% | 50.95% | 51.59% | 52.23% | 52.81% | 53.27% | 53.73% | 54.06% | 54.45% | 54.83% | 55.21% | 55.59% | 55.98% | 56.36% | 56.74% | 57.12% | 57.51% | 57.89% | 58.27% | 58.65% | 59.04% | 59.42% | 59.8% | 60.18% | 60.56% | 60.95% | 61.33% | 61.71% | 62.09% | 62.48% | 62.86% | 63.24% | 63.62% | 64.01% | 64.39% | 64.77% | 65.15% | 65.54% | 65.92% | 66.3% | 66.68% | 67.07% | 67.45% | 67.83% | 68.21% | 68.6% | 68.98% | 69.36% | 69.74% | 70.13% | 70.25% | 70.64% | 71.02% | 71.4% | 71.78% | 72.17% | 72.55% | 72.93% | 73.31% | 73.63% | 74.01% | 74.4% | 74.78% | 75.16% | 75.54% | 75.93% | 76.31% | 76.69% | 77.07% | 77.46% | 77.84% | 78.22% | 78.6% | 78.99% | 79.37% | 79.75% | 80.13% | 80.52% | 80.9% | 81.28% | 81.66% | 82.05% | 82.43% | 82.81% | 83.19% | 83.58% | 83.96% | 84.22% | 84.45% | 84.68% | 84.91% | 84.94%
2022-05-28
|  |  | Activity ID | Activity Name | Start | Finish | Original Duration | Total Float | Budgeted Total Cost | Spreadsheet Field | 2019-06-23 | 2019-06-30 | 2019-07-07 | 43660 | 43667 | 2019-07-28 | 2019-08-04 | 2019-08-11 | 2019-08-18 | 43702 | 43709 | 43716 | 43723 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 43751 | 43758 | 43765 | 43772 | 43779 | 43786 | 43793 | 43800 | 43807 | 43814 | 43821 | 43828 | 43835 | 43842 | 43849 | 43856 | 43863 | 43870 | 43877 | 43884 | 43891 | 43898 | 43905 | 43912 | 43919 | 43926 | 43933 | 43940 | 43947 | 43954 | 43961 | 43968 | 43975 | 43982 | 43989 | 43996 | 44003 | 44010 | 44017 | 44024 | 44031 | 44038 | 44045 | 44052 | 44059 | 44066 | 44073 | 44080 | 44087 | 44094 | 44101 | 44108 | 44115 | 44122 | 44129 | 44136 | 44143 | 44150 | 44157 | 44164 | 44171 | 44178 | 44185 | 44192 | 44199 | 44206 | 44213 | 44220 | 44227 | 44234 | 44241 | 44248 | 44255 | 44262 | 44269 | 44276 | 44283 | 44290 | 44297 | 44304 | 44311 | 44318 | 44325 | 44332 | 44339 | 44346 | 44353 | 44360 | 44367 | 44374 | 44381 | 44388 | 44395 | 44402 | 44409 | 44416 | 44423 | 44430 | 44437 | 44444 | 44451 | 44458 | 44465 | 44472 | 44479 | 44486 | 44493 | 44500 | 44507 | 44514 | 44521 | 44528 | 44535 | 44542 | 44549 | 44556 | 44563 | 44570 | 44577 | 44584 | 44591 | 44598 | 44605 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 44640 | 44647 | 44654 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 44731 | 44738 | 44745 | 44752 | 44759 | 44766 | 44773 | 44780 | 44787 |  |  |  |  | 12085.1
|  |  | CUTTING (EXCAVATION) |  | 23-Jun-19 A | 2022-08-15 | 948 | 0 | 3181773601% | Actual Total Cost | 293011% | 2981.57 | 2964.74 | 3292.24 | 6324.72 | 17244.83 | 1939-04-17 06:14 | 1918-12-15 05:17 | 1995-09-18 19:55 | 46497.16 | 224216.36 | 261468.66 | 261285.28 | 68641.74 | 37641.29 | 37432.32 | 37501.53 | 37502.59 | 37497.24 | 37495.45 | 37495.45 | 37499.42 | 37503.19 | 28612.5 | 10831.11 | 10831.11 | 10831.11 | 10862.06 | 10904.6 | 33432.32 | 62123.73 | 47523.8 | 18396.59 | 105442.71 | 279293.6 | 452532.05 | 279465.13 | 19219.02 | 17351.99 | 17353.11 | 17369.94 | 106211.51 | 152447.47 | 78790.95 | 48078.39 | 438013.78 | 764385.52 | 490286.56 | 284265.09 | 568533 | 568521.35 | 568527.88 | 568625.67 | 569610.45 | 524175.81 | 524300.87 | 537070.76 | 365551 | 364512.52 | 519229.95 | 574347.51 | 610542.93 | 610602.47 | 611004.25 | 635342.79 | 578044.85 | 751258.41 | 751310.5 | 751198.03 | 726346.42 | 676401.97 | 672278.97 | 676626.11 | 701264.52 | 561106.09 | 491026.87 | 491026.87 | 491026.87 | 449743.29 | 420416.43 | 354075.9 | 354281.89 | 353282.25 | 316495.01 | 292694.22 | 60343.4 | 572844.45 | 168392.55 | 10242.48 | 10242.48 | 10242.48 | 10242.48 | 10242.48 | 10242.48 | 10242.31 | 10242.28 | 42702.49 | 147910.79 | 147910.79 | 147910.79 | 147910.79 | 147910.79 | 125884.23 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 3414.09 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 8535.23 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10242.28 | 10258.28 | 10274.28 | 10242.28 | 139889.41 | 170460.9 | 162419.77 | 140393.33 | 139912.17 | 117138.68 | 160353.32 | 108094.92 | 377299.48 | [18 empty] | 32330384.58
|  |  | CUTTING (EXCAVATION) |  | 23-Jun-19 A | 2022-08-15 | 948 | 0 | 31817736.01 | Cum Actual Total Cost | 2930.11 | 5911.68 | 8876.41 | 12168.66 | 18493.38 | 35738.21 | 50090.48 | 57014.7 | 91975.53 | 138472.69 | 362689.05 | 624157.71 | 885442.99 | 954084.73 | 991726.03 | 1029158.35 | 1066659.88 | 1104162.47 | 1141659.7 | 1179155.15 | 1216650.6 | 1254150.03 | 1291653.22 | 1320265.71 | 1331096.82 | 1341927.93 | 1352759.04 | 1363621.1 | 1374525.7 | 1407958.02 | 1470081.76 | 1517605.56 | 1536002.15 | 1641444.86 | 1920738.45 | 2373270.5 | 2652735.63 | 2671954.65 | 2689306.65 | 2706659.76 | 2724029.7 | 2830241.21 | 2982688.69 | 3061479.64 | 3109558.02 | 3547571.81 | 4311957.33 | 4802243.89 | 5086508.98 | 5655041.97 | 6223563.32 | 6792091.2 | 7360716.88 | 7930327.32 | 8454503.13 | 8978804 | 9515874.76 | 9881425.76 | 10245938.28 | 10765168.23 | 11339515.74 | 11950058.67 | 12560661.14 | 13171665.39 | 13807008.19 | 14385053.04 | 15136311.45 | 15887621.95 | 16638819.98 | 17365166.41 | 18041568.37 | 18713847.35 | 19390473.46 | 20091737.98 | 20652844.07 | 21143870.94 | 21634897.81 | 22125924.69 | 22575667.98 | 22996084.41 | 23350160.31 | 23704442.2 | 24057724.45 | 24374219.45 | 24666913.67 | 24727257.07 | 25300101.52 | 25468494.07 | 25478736.55 | 25488979.02 | 25499221.5 | 25509463.98 | 25519706.45 | 25529948.93 | 25540191.24 | 25550433.51 | 25593136.01 | 25741046.8 | 25888957.59 | 26036868.38 | 26184779.17 | 26332689.96 | 26458574.19 | 26468816.47 | 26479058.74 | 26489301.02 | 26499543.29 | 26509785.57 | 26513199.66 | 26523441.94 | 26533684.21 | 26543926.49 | 26554168.76 | 26564411.04 | 26574653.31 | 26584895.59 | 26595137.86 | 26603673.09 | 26613915.37 | 26624157.64 | 26634399.92 | 26644642.19 | 26654884.47 | 26665126.74 | 26675369.02 | 26685611.29 | 26695853.57 | 26706095.85 | 26716338.12 | 26726580.4 | 26736822.67 | 26747064.95 | 26757307.22 | 26767549.5 | 26777791.77 | 26788034.05 | 26798276.32 | 26808518.6 | 26818760.87 | 26829019.15 | 26839293.42 | 26849535.7 | 26989425.11 | 27159886.01 | 27322305.78 | 27462699.11 | 27602611.28 | 27719749.95 | 27880103.28 | 27988198.19 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68 | 28365497.68
27.65%
[11 empty] | 2022-05-08: 89.15% |  |  |  |  | 69532%
|  |  | Activity ID | Activity Name | Start | Finish | Original Duration | Total Float | Budgeted Total Cost | Spreadsheet Field | 2019-06-23 | 2019-06-30 | 2019-07-07 | 43660 | 43667 | 2019-07-28 | 2019-08-04 | 2019-08-11 | 2019-08-18 | 43702 | 43709 | 43716 | 43723 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 43751 | 43758 | 43765 | 43772 | 43779 | 43786 | 43793 | 43800 | 43807 | 43814 | 43821 | 43828 | 43835 | 43842 | 43849 | 43856 | 43863 | 43870 | 43877 | 43884 | 43891 | 43898 | 43905 | 43912 | 43919 | 43926 | 43933 | 43940 | 43947 | 43954 | 43961 | 43968 | 43975 | 43982 | 43989 | 43996 | 44003 | 44010 | 44017 | 44024 | 44031 | 44038 | 44045 | 44052 | 44059 | 44066 | 44073 | 44080 | 44087 | 44094 | 44101 | 44108 | 44115 | 44122 | 44129 | 44136 | 44143 | 44150 | 44157 | 44164 | 44171 | 44178 | 44185 | 44192 | 44199 | 44206 | 44213 | 44220 | 44227 | 44234 | 44241 | 44248 | 44255 | 44262 | 44269 | 44276 | 44283 | 44290 | 44297 | 44304 | 44311 | 44318 | 44325 | 44332 | 44339 | 44346 | 44353 | 44360 | 44367 | 44374 | 44381 | 44388 | 44395 | 44402 | 44409 | 44416 | 44423 | 44430 | 44437 | 44444 | 44451 | 44458 | 44465 | 44472 | 44479 | 44486 | 44493 | 44500 | 44507 | 44514 | 44521 | 44528 | 44535 | 44542 | 44549 | 44556 | 44563 | 44570 | 44577 | 44584 | 44591 | 44598 | 44605 | 44612 | 44619 | 44626 | 44633 | 44640 | 44647 | 44654 | 44661 | 44668 | 44675 | 44682 | 4468900% | 44696 | 44703 | 44710 | 44717 | 44724 | 44731 | 44738 | 44745 | 44752 | 44759
|  |  | Preliminaries |  | 23-Jun-19 A | 2022-07-16 | 359 | 26 | 7080210.57 | Actual Total Cost | 26487.67 | 26936.61 | 29223.98 | 44581.92 | 58160.06 | 51408.06 | 26915.37 | 9736.35 | 40033.47 | 45446.54 | 45446.54 | 31916 | 58829.76 | 61366.76 | 73640.11 | 74074.89 | 74292.28 | 74292.28 | 74292.28 | 74292.28 | 74292.28 | 74292.28 | 74292.28 | 77691.36 | 81090.44 | 81090.44 | 75425.3 | 74292.28 | 74292.28 | 74292.28 | 74292.28 | 74292.28 | 74292.28 | 90134.73 | 89126.99 | 83479.27 | 94531.85 | 112025.45 | 81206.84 | 81206.84 | 81206.84 | 81206.84 | 60072.23 | 58069.82 | 48057.79 | 48057.79 | 48057.79 | 48057.79 | 30036.12 | 60072.23 | 60072.23 | 49027.02 | 32076.63 | 45129.07 | 45129.07 | 45129.07 | 45129.07 | 30086.04 | 30086.04 | 45129.07 | 45129.07 | 45129.07 | 38805.23 | 32481.39 | 32481.39 | 22447.18 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 8978.87 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 22447.18 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 26936.61 | 25140.84 | 18182.21 | 16161.97 | 16161.97 | 16161.97 | 8978.87 | 17957.74
|  |  | Preliminaries |  | 23-Jun-19 A | 2022-07-16 | 359 | 26 | 7080210.57 | Cum Actual Total Cost | 26487.67 | 53424.28 | 82648.26 | 127230.18 | 185390.24 | 236798.3 | 263713.67 | 273450.02 | 313483.48 | 358930.02 | 404376.56 | 436292.56 | 495122.32 | 556489.08 | 630129.19 | 704204.08 | 778496.36 | 852788.64 | 927080.92 | 1001373.19 | 1075665.47 | 1149957.75 | 1224250.02 | 1301941.38 | 1383031.82 | 1464122.26 | 1539547.56 | 1613839.84 | 1688132.12 | 1762424.4 | 1836716.67 | 1911008.95 | 1985301.23 | 2075435.96 | 2164562.95 | 2248042.22 | 2342574.06 | 2454599.51 | 2535806.35 | 2617013.19 | 2698220.02 | 2779426.86 | 2839499.09 | 2897568.92 | 2945626.7 | 2993684.49 | 3041742.27 | 3089800.06 | 3119836.17 | 3179908.41 | 3239980.64 | 3289007.66 | 3321084.29 | 3366213.36 | 3411342.43 | 3456471.49 | 3501600.56 | 3531686.6 | 3561772.64 | 3606901.71 | 3652030.78 | 3697159.84 | 3735965.07 | 3768446.47 | 3800927.86 | 3823375.03 | 3850311.64 | 3877248.25 | 3904184.87 | 3931121.48 | 3958058.09 | 3984994.7 | 4011931.31 | 4038867.92 | 4065804.53 | 4092741.14 | 4119677.75 | 4146614.36 | 4173550.97 | 4200487.58 | 4227424.19 | 4254360.8 | 4281297.41 | 4308234.02 | 4335170.63 | 4362107.24 | 4389043.85 | 4415980.46 | 4442917.08 | 4469853.69 | 4496790.3 | 4523726.91 | 4550663.52 | 4577600.13 | 4604536.74 | 4631473.35 | 4658409.96 | 4685346.57 | 4712283.18 | 4739219.79 | 4766156.4 | 4793093.01 | 4820029.62 | 4846966.23 | 4873902.84 | 4900839.45 | 4927776.06 | 4954712.68 | 4963691.55 | 4990628.16 | 5017564.77 | 5044501.38 | 5071437.99 | 5098374.6 | 5125311.21 | 5152247.82 | 5179184.43 | 5201631.6 | 5228568.22 | 5255504.83 | 5282441.44 | 5309378.05 | 5336314.66 | 5363251.27 | 5390187.88 | 5417124.49 | 5444061.1 | 5470997.71 | 5497934.32 | 5524870.93 | 5551807.54 | 5578744.15 | 5605680.76 | 5632617.37 | 5659553.98 | 5686490.59 | 5713427.2 | 5740363.82 | 5767300.43 | 5794237.04 | 5821173.65 | 5848110.26 | 5875046.87 | 5901983.48 | 5927124.31 | 5945306.53 | 5961468.49 | 5977630.46 | 5993792.43 | 6002771.3 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04 | 6020729.04
85.04%
[180 empty] | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16
[180 empty] | 26717317.93 | 26717317.93 | 26717317.93 | 26717317.93 | 26717317.93 | 26717317.93
2022-07-02
27185737.53
[180 empty] | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09
[180 empty] | 27373740.41 | 27373740.41 | 27373740.41 | 27373740.41 | 27373740.41 | 27373740.41 | 27373740.41 | 27373740.41 | 27373740.41
[180 empty] | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25
[180 empty] | 5798113.71 | 5798113.71 | 5798113.71 | 5798113.71 | 5798113.71 | 5798113.71 | 5798113.71
[180 empty] | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16 | 2022-07-23
[180 empty] | 27883814.45 | 27883814.45 | 27883814.45 | 27883814.45 | 27883814.45 | 27883814.45 | 27883814.45 | 27883814.45 | 27883814.45 | 27883814.45
Formulas:
Date = IFERROR(IF(WORKDAY.INTL([Date, row above],4,7)>Timeline[Forecast End Date],"",WORKDAY.INTL([Date, row above],4,7)),"")

## Manpower S-Curve
Date | Weekly Plan | Weekly forecast | Weekly Actual | Cumulative Plan | Cummulative forecast | Cumulative Actual
2019-06-27 | 20 | 15 | 15 | 90 | 90 | 90
2019-07-04 | 20 | 15 | 15 | 180 | 180 | 180
2019-07-11 | 20 | 15 | 15 | 270 | 270 | 270
2019-07-18 | 20 | 15 | 15 | 360 | 360 | 360
2019-07-25 | 20 | 15 | 15 | 450 | 450 | 450
2019-08-01 | 20 | 15 | 15 | 540 | 540 | 540
2019-08-08 | 25 | 20 | 20 | 660 | 660 | 660
2019-08-15 | 25 | 20 | 20 | 780 | 780 | 780
2019-08-22 | 25 | 20 | 20 | 900 | 900 | 900
2019-08-29 | 25 | 20 | 20 | 1020 | 1020 | 1020
2019-09-05 | 40 | 25 | 25 | 1170 | 1170 | 1170
2019-09-12 | 40 | 25 | 25 | 1320 | 1320 | 1320
2019-09-19 | 40 | 25 | 25 | 1470 | 1470 | 1470
2019-09-26 | 40 | 25 | 25 | 1620 | 1620 | 1620
2019-10-03 | 60 | 30 | 30 | 1800 | 1800 | 1800
2019-10-10 | 60 | 30 | 30 | 1980 | 1980 | 1980
2019-10-17 | 60 | 30 | 30 | 2160 | 2160 | 2160
2019-10-24 | 60 | 30 | 30 | 2340 | 2340 | 2340
2019-10-31 | 60 | 30 | 30 | 2520 | 2520 | 2520
2019-11-07 | 100 | 35 | 35 | 2730 | 2730 | 2730
2019-11-14 | 100 | 35 | 35 | 2940 | 2940 | 2940
2019-11-21 | 100 | 35 | 35 | 3150 | 3150 | 3150
2019-11-28 | 100 | 35 | 35 | 3360 | 3360 | 3360
2019-12-05 | 130 | 40 | 40 | 3600 | 3600 | 3600
2019-12-12 | 130 | 40 | 40 | 3840 | 3840 | 3840
2019-12-19 | 130 | 40 | 40 | 4080 | 4080 | 4080
2019-12-26 | 130 | 40 | 40 | 4320 | 4320 | 4320
2020-01-02 | 130 | 40 | 40 | 4560 | 4560 | 4560
2020-01-09 | 160 | 45 | 45 | 4830 | 4830 | 4830
2020-01-16 | 160 | 45 | 45 | 5100 | 5100 | 5100
2020-01-23 | 160 | 45 | 45 | 5370 | 5370 | 5370
2020-01-30 | 160 | 45 | 45 | 5640 | 5640 | 5640
2020-02-06 | 170 | 50 | 50 | 5940 | 5940 | 5940
2020-02-13 | 170 | 50 | 50 | 6240 | 6240 | 6240
2020-02-20 | 170 | 50 | 50 | 6540 | 6540 | 6540
2020-02-27 | 170 | 50 | 50 | 6840 | 6840 | 6840
2020-03-05 | 180 | 55 | 55 | 7170 | 7170 | 7170
2020-03-12 | 180 | 55 | 55 | 7500 | 7500 | 7500
2020-03-19 | 180 | 55 | 55 | 7830 | 7830 | 7830
2020-03-26 | 180 | 55 | 55 | 8160 | 8160 | 8160
2020-04-02 | 180 | 55 | 55 | 8490 | 8490 | 8490
2020-04-09 | 190 | 60 | 60 | 8850 | 8850 | 8850
2020-04-16 | 190 | 60 | 60 | 9210 | 9210 | 9210
2020-04-23 | 190 | 60 | 60 | 9570 | 9570 | 9570
2020-04-30 | 190 | 60 | 60 | 9930 | 9930 | 9930
2020-05-07 | 180 | 65 | 65 | 10320 | 10320 | 10320
2020-05-14 | 180 | 65 | 65 | 10710 | 10710 | 10710
2020-05-21 | 180 | 65 | 65 | 11100 | 11100 | 11100
2020-05-28 | 180 | 65 | 65 | 11490 | 11490 | 11490
2020-06-04 | 150 | 70 | 70 | 11910 | 11910 | 11910
2020-06-11 | 150 | 70 | 70 | 12330 | 12330 | 12330
2020-06-18 | 150 | 70 | 70 | 12750 | 12750 | 12750
2020-06-25 | 150 | 70 | 70 | 13170 | 13170 | 13170
2020-07-02 | 150 | 70 | 70 | 13590 | 13590 | 13590
2020-07-09 | 140 | 82 | 82 | 14082 | 14082 | 14082
2020-07-16 | 140 | 82 | 82 | 14574 | 14574 | 14574
2020-07-23 | 140 | 82 | 82 | 15066 | 15066 | 15066
2020-07-30 | 140 | 82 | 82 | 15558 | 15558 | 15558
2020-08-06 | 130 | 80 | 80 | 16038 | 16038 | 16038
2020-08-13 | 130 | 80 | 80 | 16518 | 16518 | 16518
2020-08-20 | 130 | 80 | 80 | 16998 | 16998 | 16998
2020-08-27 | 130 | 80 | 80 | 17478 | 17478 | 17478
2020-09-03 | 100 | 85 | 85 | 17988 | 17988 | 17988
2020-09-10 | 100 | 85 | 85 | 18498 | 18498 | 18498
2020-09-17 | 100 | 85 | 85 | 19008 | 19008 | 19008
2020-09-24 | 100 | 85 | 85 | 19518 | 19518 | 19518
2020-10-01 | 100 | 85 | 85 | 20028 | 20028 | 20028
2020-10-08 | 90 | 132 | 132 | 20820 | 20820 | 20820
2020-10-15 | 90 | 132 | 132 | 21612 | 21612 | 21612
2020-10-22 | 90 | 132 | 132 | 22404 | 22404 | 22404
2020-10-29 | 90 | 132 | 132 | 23196 | 23196 | 23196
2020-11-05 | 80 | 100 | 100 | 23796 | 23796 | 23796
2020-11-12 | 80 | 100 | 100 | 24396 | 24396 | 24396
2020-11-19 | 80 | 100 | 100 | 24996 | 24996 | 24996
2020-11-26 | 80 | 100 | 100 | 25596 | 25596 | 25596
2020-12-03 | 60 | 90 | 90 | 26136 | 26136 | 26136
2020-12-10 | 60 | 90 | 90 | 26676 | 26676 | 26676
2020-12-17 | 60 | 90 | 90 | 27216 | 27216 | 27216
2020-12-24 | 60 | 90 | 90 | 27756 | 27756 | 27756
2020-12-31 | 60 | 90 | 90 | 28296 | 28296 | 28296
2021-01-07 | 40 | 88 | 88 | 28824 | 28824 | 28824
2021-01-14 | 40 | 88 | 88 | 29352 | 29352 | 29352
2021-01-21 | 40 | 88 | 88 | 29880 | 29880 | 29880
2021-01-28 | 40 | 88 | 88 | 30408 | 30408 | 30408
2021-02-04 | 62 |  | 62 | 30780 | 30780 | 30780
2021-02-11 | 62 |  | 62 | 31152 | 31152 | 31152
2021-02-18 | 62 |  | 62 | 31524 | 31524 | 31524
2021-02-25 | 62 |  | 62 | 31896 | 31896 | 31896
2021-03-04 | 60 |  | 60 | 32256 | 32256 | 32256
2021-03-11 | 60 |  | 60 | 32616 | 32616 | 32616
2021-03-18 | 60 |  | 60 | 32976 | 32976 | 32976
2021-03-25 | 60 |  | 60 | 33336 | 33336 | 33336
2021-04-01 | 60 |  | 60 | 33696 | 33696 | 33696
2021-04-08 | 59 |  | 59 | 34050 | 34050 | 34050
2021-04-15 | 59 |  | 59 | 34404 | 34404 | 34404
2021-04-22 | 59 |  | 59 | 34758 | 34758 | 34758
2021-04-29 | 59 |  | 59 | 35112 | 35112 | 35112
2021-05-06 | 78 |  | 78 | 35580 | 35580 | 35580
2021-05-13 | 78 |  | 78 | 36048 | 36048 | 36048
2021-05-20 | 78 |  | 78 | 36516 | 36516 | 36516
2021-05-27 | 78 |  | 78 | 36984 | 36984 | 36984
2021-06-03 | 79 |  | 79 | 37458 | 37458 | 37458
2021-06-10 | 79 |  | 79 | 37932 | 37932 | 37932
2021-06-17 | 79 |  | 79 | 38406 | 38406 | 38406
2021-06-24 | 79 |  | 79 | 38880 | 38880 | 38880
2021-07-01 | 79 |  | 79 | 39354 | 39354 | 39354
2021-07-08 | 42 |  | 42 | 39606 | 39606 | 39606
2021-07-15 | 42 |  | 42 | 39858 | 39858 | 39858
2021-07-22 | 42 |  | 42 | 40110 | 40110 | 40110
2021-07-29 | 42 |  | 42 | 40362 | 40362 | 40362
2021-08-05 | 25 |  | 25 | 40512 | 40512 | 40512
2021-08-12 | 25 |  | 25 | 40662 | 40662 | 40662
2021-08-19 | 25 |  | 25 | 40812 | 40812 | 40812
2021-08-26 | 25 |  | 25 | 40962 | 40962 | 40962
2021-09-02 | 25 |  | 25 | 41112 | 41112 | 41112
2021-09-09 | 26 |  | 26 | 41268 | 41268 | 41268
2021-09-16 | 26 |  | 26 | 41424 | 41424 | 41424
2021-09-23 | 26 |  | 26 | 41580 | 41580 | 41580
2021-09-30 | 26 |  | 26 | 41736 | 41736 | 41736
2021-10-07 | 20 |  | 20 | 41856 | 41856 | 41856
2021-10-14 | 20 |  | 20 | 41976 | 41976 | 41976
2021-10-21 | 20 |  | 20 | 42096 | 42096 | 42096
2021-10-28 | 20 |  | 20 | 42216 | 42216 | 42216
2021-11-04 | 10 |  | 10 | 42276 | 42276 | 42276
2021-11-11 | 10 |  | 10 | 42336 | 42336 | 42336
2021-11-18 | 12 |  | 12 | 42408 | 42408 | 42408
2021-11-25 | 12 |  | 12 | 42480 | 42480 | 42480
2021-12-02 | 12 |  | 12 | 42552 | 42552 | 42552
2021-12-09 | 12 |  | 12 | 42624 | 42624 | 42624
2021-12-16 | 12 |  | 12 | 42696 | 42696 | 42696
2021-12-23 | 7 |  | 7 | 42738 | 42738 | 42738
2021-12-30 | 6 |  | 6 | 42774 | 42774 | 42774
2022-01-06 | 6 |  | 6 | 42810 | 42810 | 42810
2022-01-13 | 6 |  | 6 | 42846 | 42846 | 42846
2022-01-20 | 6 |  | 6 | 42882 | 42882 | 42882
2022-01-27 | 6 |  | 6 | 42918 | 42918 | 42918
2022-02-03 | 6 |  | 6 | 42954 | 42954 | 42954
2022-02-10 | 11 |  | 11 | 43020 | 43020 | 43020
2022-02-17 | 11 |  | 11 | 43086 | 43031 | 43031
2022-02-24 | 11 |  | 11 | 43152 | 43042 | 43042
2022-03-03 | 21 |  | 21 | 43173 | 43063 | 43063
2022-03-10 | 21 |  | 21 | 43194 | 43084 | 43084
2022-03-17 | 65 |  | 46 | 43259 | 43130 | 43130
2022-03-24 | 65 |  | 52 | 43324 | 43182 | 43182
2022-03-31 | 65 |  | 53 | 43389 | 43235 | 43235
2022-04-07 | 65 |  | 57 | 43454 | 43292 | 43292
2022-04-14 | 65 |  | 57 | 43519 | 43349 | 43349
2022-04-21 | 65 |  | 58 | 43584 | 43407 | 43407
2022-04-28 | 65 |  | 79 | 43649 | 43486 | 43486
2022-05-05 | 65 |  | 79 | 43714 | 43565 | 43565
2022-05-12 | 65 |  | 79 | 43779 | 43644 | 43644
2022-05-19 | 65 |  |  | 43844
2022-05-26 | 21 |  |  | 43865

## Cashflow & Variations
Report Week Date
2022-05-12
2022-05-05
| Contract FC & EAC ¦ DATA INPUT | [8 empty] | 0 | 0 | 0 | 0 | Monthly Cashflow ¦ DATA INPUT |  |  |  |  | Current Contract Vaule | Original Contract Vaule | Approved Variations | Potiental Cost Impact |  |  |  |  | 29167864 |  | 10693915 |  | 39861779
[19 empty] | 39.8618 | 29.1679 | 10.6939 | 0
| Last Report Date | This Report Date | Weekly Plan Cashflow | Weekly Actual Cashflow | Cumulative Planned Cashflow | Cumulative Actual Cashlow | Pending Variations | Approved Variations | EWs | Last Period FC | This Period FC | Last Period EAC | This Period EAC | Date | Monthly Plan Cashflow | Monthly Actual Cashflow | Cumulative Planned Cashflow | Cumulative Actual Cashlow | [7 empty] | % Increase in Contract Vaule |  |  | % Certified to Date (inc. advance) | [6 empty] | PLANNED | ACTUAL | FORECAST
0 |  | 4363900% | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 2019-06-23 | 0.22084 | 0.33664 | 0.22084 | 0.033664 | [7 empty] | 36.66% |  |  | 118.2% | [5 empty] | 2019-01-01
0 | 4363900% | 4364300% | 0.15682 | 0.023901 | 0.15682 | 0.023901 |  |  |  | 0 | 0.15241 | 0 | 0 | 2019-07-31 | 0.95616 | 2.1491 | 1.177 | 0.24858 | [16 empty] | 2019-02-01
0 | 4364300% | 4365000% | 0.34884 | 0.029278 | 0.34884 | 0.053179 |  |  |  | 0.15241 | 0.08393 | 0 | 0 | 2019-08-31 | 1.0416 | 2.581 | 2.2186 | 0.50668 | [16 empty] | 2019-03-04
0 | 4365000% | 4365700% | 0.54081 | 0.02923 | 0.54081 | 0.082409 |  |  |  | 0.08393 | 0.054048 | 0 | 0 | 2019-09-30 | 1.9734 | 10.7712 | 4.1921 | 1.5838 | [16 empty] | 2019-04-04
0 | 4365700% | 4366400% | 0.7518 | 0.044596 | 0.7518 | 0.127 |  |  |  | 0.054048 | 0.059318 | 0 | 0 | 2019-10-31 | 1.3757 | 5.3379 | 5.5678 | 2.1176 | [16 empty] | 2019-05-05
0 | 4366400% | 4367100% | 0.98344 | 0.0614 | 0.98344 | 0.1884 |  |  |  | 0.059318 | 0.062434 | 0 | 0 | 2019-11-30 | 1.1653 | 4.9576 | 6.7331 | 2.6133 | [16 empty] | 2019-06-05 | 85500.24 |  |  |  | 0.21661
0 | 4367100% | 4367800% | 1.213 | 0.070401 | 1.213 | 0.25881 |  |  |  | 0.062434 | 0.058039 | 0 | 0 | 2019-12-31 | 1.156 | 4.5226 | 7.8891 | 3.0656 | [16 empty] | 2019-07-06 | 263343.97 |  |  |  | 0.21661
0 | 4367800% | 4368500% | 1.4233 | 0.05106 | 1.4233 | 0.30987 |  |  |  | 0.058039 | 0.035874 | 0 | 0 | 2020-01-31 | 0.41362 | 5.1043 | 8.3027 | 3.576 | [16 empty] | 2019-08-06 | 3156389.3 |  |  |  | 0.21661
0 | 4368500% | 4369200% | 1.4743 | 0.009139 | 1.4743 | 0.319 |  |  |  | 0.035874 | 0.0061988 | 0 | 0 | 2020-02-29 | 1.2761 | 12.3797 | 9.5787 | 4.814 | [16 empty] | 2019-09-06 | 8949989.59 |  |  |  | 0.21661
0 | 4369200% | 4369900% | 1.802 | 0.073512 | 1.802 | 0.39252 |  |  |  | 0.0061988 | 0.040795 | 0 | 0 | 2020-03-31 | 0.59996 | 7.8208 | 10.1787 | 5.5961 | [16 empty] | 2019-10-07 | 5747545.79 |  |  |  | 0.21661
0 | 4369900% | 4370600% | 2.1605 | 0.099429 | 2.1605 | 0.49194 |  |  |  | 0.040795 | 0.046022 | 0 | 0 | 2020-04-30 | 0.32513 | 6.9204 | 10.5038 | 6.2881 | [16 empty] | 2019-11-07 | 6140901.51 |  |  |  | 0.21661
0 | 4370600% | 4371300% | 2.6897 | 0.23782 | 2.6897 | 0.72976 |  |  |  | 0.046022 | 0.088417 | 0 | 0 | 2020-05-31 | 4.5445 | 22.9486 | 15.0483 | 8.583 | [16 empty] | 2019-12-08 | 3495773.61 | 1516238.81 |  | 1.5162 | 0.21661
0 | 4371300% | 4372000% | 3.2904 | 0.30232 | 3.2904 | 1.0321 |  |  |  | 0.088417 | 0.09188 | 0 | 0 | 2020-06-30 | 5.131 | 27.0636 | 20.1793 | 11.2893 | [16 empty] | 2020-01-08 | 1198745.94 |  |  |  | 0.7497
0 | 4372000% | 4372700% | 3.7794 | 0.3196 | 3.7794 | 1.3517 |  |  |  | 0.09188 | 0.084564 | 0 | 0 | 2020-07-31 | 3.0377 | 24.5162 | 23.2169 | 13.741 | [16 empty] | 2020-02-08 | 129674.05 |  |  |  | 0.7497
0 | 4372700% | 4373400% | 4.0373 | 0.17303 | 4.0373 | 1.5247 |  |  |  | 0.084564 | 0.042857 | 0 | 0 | 2020-08-31 | 2.3128 | 24.7906 | 25.5297 | 16.22 | [16 empty] | 2020-03-10 |  | 2249108.84 |  | 2.2491 | 0.7497
0 | 4373400% | 4374100% | 4.3468 | 0.11819 | 4.3468 | 1.6429 |  |  |  | 0.042857 | 0.027191 | 0 | 0 | 2020-09-30 | 3.3082 | 28.8871 | 28.8379 | 19.1087 | [16 empty] | 2020-04-10 |  |  |  |  | 1.106
0 | 4374100% | 4374800% | 4.6566 | 0.11839 | 4.6566 | 1.7613 |  |  |  | 0.027191 | 0.025424 | 0 | 0 | 2020-10-31 | 1.6202 | 32.9981 | 30.4581 | 22.4085 | [16 empty] | 2020-05-11 |  |  |  |  | 1.106
0 | 4374800% | 4375500% | 4.9669 | 0.11876 | 4.9669 | 1.8801 |  |  |  | 0.025424 | 0.023911 | 0 | 0 | 2020-11-30 | 0.15636 | 28.8788 | 30.6145 | 25.2964 | [16 empty] | 2020-06-11 |  | 3318077.59 |  | 3.3181 | 1.106
0 | 4375500% | 4376200% | 5.2711 | 0.11876 | 5.2711 | 1.9988 |  |  |  | 0.023911 | 0.022531 | 0 | 0 | 2020-12-31 | 0.22527 | 22.3654 | 30.8397 | 27.533 | [16 empty] | 2020-07-12 |  | 1633813.4 |  | 1.6338 | 1.6338
0 | 4376200% | 4376900% | 5.5678 | 0.11876 | 5.5678 | 2.1176 |  |  |  | 0.022531 | 0.02133 | 0 | 0 | 2021-01-31 | 0.065022 | 16.0411 | 30.9048 | 29.1371 | [16 empty] | 2020-08-12 |  | 2537619.32 |  | 2.5376 | 2.5376
0 | 4376900% | 4377600% | 5.8645 | 0.11876 | 5.8645 | 2.2363 |  |  |  | 0.02133 | 0.02025 | 0 | 0 | 2021-02-28 | 0.060021 | 11.4755 | 30.9648 | 30.2846 | [16 empty] | 2020-09-12 |  | 5361859.87 |  | 5.3619 | 5.3619
0 | 4377600% | 4378300% | 6.1607 | 0.11882 | 6.1607 | 2.3552 |  |  |  | 0.02025 | 0.019287 | 0 | 0 | 2021-03-31 | 0.067523 | 1.6336 | 31.0323 | 30.448 | [16 empty] | 2020-10-13 |  | 4298226.63 |  | 4.2982 | 4.2982
0 | 4378300% | 4379000% | 6.4248 | 0.11912 | 6.4248 | 2.4743 |  |  |  | 0.019287 | 0.018541 | 0 | 0 | 2021-04-30 | 0.12422 | 1.6078 | 31.1565 | 30.6088 | [16 empty] | 2020-11-13 |  | 3169495.02 |  | 3.1695 | 3.1695
0 | 4379000% | 4379700% | 6.689 | 0.1192 | 6.689 | 2.5935 |  |  |  | 0.018541 | 0.017821 | 0 | 0 | 2021-05-31 | 0.966 | 7.8287 | 32.1225 | 31.3916 | [16 empty] | 2020-12-14 |  | 3140790.47 |  | 3.1408 | 3.1408
0 | 4379700% | 4380400% | 6.9557 | 0.11692 | 6.9557 | 2.7104 |  |  |  | 0.017821 | 0.01681 | 0 | 0 | 2021-06-30 | 0.065022 | 3.6473 | 32.1875 | 31.7564 | Planned | Actual | Variance | [13 empty] | 2021-01-14 |  | 1165759.45 |  | 1.1658 | 1.1658
0 | 4380400% | 4381100% | 7.2268 | 0.099228 | 7.2268 | 2.8096 |  |  |  | 0.01681 | 0.01373 | 0 | 0 | 2021-07-31 | 0.055019 | 1.3311 | 32.2426 | 31.8895 | 39.8618 | 344.9829 | 305.1211 | [13 empty] | 2021-02-14 |  |  |  |  | 0.90839
0 | 4381100% | 4381800% | 7.4951 | 0.099283 | 7.4951 | 2.9089 |  |  |  | 0.01373 | 0.013246 | 0 | 0 | 2021-08-31 | 0.90312 | 1.6335 | 33.1457 | 32.0528 | [16 empty] | 2021-03-17 |  | 1816780.67 |  | 1.8168 | 0.90839
0 | 4381800% | 4382500% | 7.756 | 0.094911 | 7.756 | 3.0038 |  |  |  | 0.013246 | 0.012237 | 0 | 0 | 2021-09-30 | 0.023607 | 1.5125 | 33.1693 | 32.2041 | Including Adv. Payment | 91 | #VALUE! | [13 empty] | 2021-04-17 |  |  |  |  | 0.6287
0 | 4382500% | 4383200% | 7.9132 | 0.092667 | 7.9132 | 3.0965 |  |  |  | 0.012237 | 0.01171 | 0 | 0 | 2021-10-31 | 0 | 1.573 | 33.1693 | 32.3614 | [16 empty] | 2021-05-18 |  | 1257402.97 |  | 1.2574 | 0.6287
0 | 4383200% | 4383900% | 7.9858 | 0.092719 | 7.9858 | 3.1892 |  |  |  | 0.01171 | 0.01161 | 0 | 0 | 2021-11-30 | 0 | 1.573 | 33.1693 | 32.5187 | [16 empty] | 2021-06-18 |  |  |  |  | 0.18595
0 | 4383900% | 4384600% | 8.0745 | 0.10671 | 8.0745 | 3.2959 |  |  |  | 0.01161 | 0.013216 | 0 | 0 | 2021-12-31 | 1.3555 | 1.573 | 34.5248 | 32.676 | [16 empty] | 2021-07-19 |  |  |  |  | 0.18595
0 | 4384600% | 4385300% | 8.2024 | 0.14371 | 8.2024 | 3.4397 |  |  |  | 0.013216 | 0.017521 | 0 | 0 | 2022-01-31 | 0 | 1.6335 | 34.5248 | 32.8393 | [16 empty] | 2021-08-19 |  |  |  |  | 0.18595
0 | 4385300% | 4386000% | 8.3027 | 0.13639 | 8.3027 | 3.576 |  |  |  | 0.017521 | 0.016427 | 0 | 0 | 2022-02-28 | 0.085479 | 1.4525 | 34.6102 | 32.9846 | [16 empty] | 2021-09-19 |  |  |  |  | 0.18595
0 | 4386000% | 4386700% | 8.3718 | 0.10002 | 8.3718 | 3.6761 |  |  |  | 0.016427 | 0.011947 | 0 | 0 | 2022-03-31 | 2.6101 | 5.5294 | 37.2204 | 33.5375 | [16 empty] | 2021-10-20 |  |  |  |  | 0.18595
0 | 4386700% | 4387400% | 8.5054 | 0.15597 | 8.5054 | 3.832 |  |  |  | 0.011947 | 0.018338 | 0 | 0 | 2022-04-30 | 1.5026 | 7.9183 | 38.7229 | 34.4822 | [16 empty] | 2021-11-20 |  | 1115706.37 |  | 1.1157 | 0.18595
0 | 4387400% | 4388100% | 8.9313 | 0.37762 | 8.9313 | 4.2097 |  |  |  | 0.018338 | 0.042281 | 0 | 0 | 2022-05-31 | 1.1388 | 1.6891 | 39.8618 | 36.3006 | [16 empty] | 2021-12-21 |  | 114890.75 |  |  | 0.18595
0 | 4388100% | 4388800% | 9.4969 | 0.54275 | 9.4969 | 4.7524 |  |  |  | 0.042281 | 0.057151 | 0 | 0 | [23 empty] | 32695770.16 |  |  | 32.7668
0 | 4388800% | 4389500% | 9.81 | 0.37849 | 9.81 | 5.1309 |  |  |  | 0.057151 | 0.038582 | 0 | 0
0 | 4389500% | 4390200% | 9.9392 | 0.18427 | 9.9392 | 5.3152 |  |  |  | 0.038582 | 0.018539 | 0 | 0
0 | 4390200% | 4390900% | 10.036 | 0.10553 | 10.036 | 5.4207 |  |  |  | 0.018539 | 0.010515 | 0 | 0
0 | 4390900% | 4391600% | 10.1247 | 0.10526 | 10.1247 | 5.5259 |  |  |  | 0.010515 | 0.010396 | 0 | 0
0 | 4391600% | 4392300% | 10.1987 | 0.10522 | 10.1987 | 5.6312 |  |  |  | 0.010396 | 0.010317 | 0 | 0
0 | 4392300% | 4393000% | 10.4589 | 0.17186 | 10.4589 | 5.803 |  |  |  | 0.010317 | 0.016432 | 0 | 0
0 | 4393000% | 4393700% | 10.4761 | 0.22273 | 10.4761 | 6.0258 |  |  |  | 0.016432 | 0.021261 | 0 | 0
0 | 4393700% | 4394400% | 10.4915 | 0.16277 | 10.4915 | 6.1885 |  |  |  | 0.021261 | 0.015515 | 0 | 0 | [5 empty] | Activity ID | Resource ID Name | Activity Name | Start | Finish | Price / Unit | Budgeted Units | sar UNIT | Spreadsheet Field | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01
0 | 4394400% | 4395100% | 10.5038 | 0.099595 | 10.5038 | 6.2881 |  |  |  | 0.015515 | 0.0094818 | 0 | 0 | [5 empty] | Project: AM-BL-UP TB1100101 EW P1-BL-PO- UP- 20220505 |  |  | 23-Jun-19 A | 44781 |  | --- | 0 | Actual Cost | 34570.24 | 218455.26 | 260859.01 | 1080405.61 | 537331.53 | 499038.89 | 455807.79 | 514492.2 | 1242599.28 | 787069.75 | 696627.19 | 2298408.84 | 2711167.64 | 2456240.17 | 2483501.76 | 2893332.97 | 3304622.01 | 2892689.67 | 2241537.68 | 1608914.61 | 1151987.82 | 168357.9 | 165401.87 | 787865.31 | 369542.51 | 137179.77 | 168348.17 | 155876.52 | 162111.58 | 162111.58 | 162111.58 | 168346.64 | 149689.46 | 563716.61 | 791834.81 | 129383.65
0 | 4395100% | 4395800% | 11.1281 | 0.40479 | 11.1281 | 6.6929 |  |  |  | 0.0094818 | 0.036376 | 0 | 0 | [5 empty] | Project: AM-BL-UP TB1100101 EW P1-BL-PO- UP- 20220505 |  |  | 23-Jun-19 A | 44781 |  | --- | 0 | Cum Actual Cost | 34570.24 | 253025.51 | 513884.52 | 1594290.13 | 2131621.66 | 2630660.56 | 3086468.35 | 3600960.55 | 4843559.84 | 5630629.59 | 6327256.79 | 8625665.63 | 11336833.27 | 13793073.44 | 16276575.19 | 19169908.17 | 22474530.17 | 25367219.84 | 27608757.53 | 29217672.13 | 30369659.95 | 30538017.85 | 30703419.71 | 31491285.03 | 31860827.53 | 31998007.3 | 32166355.47 | 32322231.99 | 32484343.57 | 32646455.15 | 32808566.73 | 32976913.37 | 33126602.82 | 33690319.44 | 34482154.25 | 34611537.89 | 34611537.89 | 34611537.89 | 34611537.89
0 | 4395800% | 4396500% | 12.5491 | 0.78755 | 12.5491 | 7.4805 |  |  |  | 0.036376 | 0.062758 | 0 | 0
0 | 4396500% | 4397200% | 13.9302 | 0.59437 | 13.9302 | 8.0748 |  |  |  | 0.062758 | 0.042668 | 0 | 0 | [14 empty] | 2022-04-01: 7.9183; 2022-05-01: 1.2938
0 | 4397200% | 4397900% | 14.6319 | 0.29642 | 14.6319 | 8.3713 |  |  |  | 0.042668 | 0.020259 | 0 | 0 |  | 10.6939
0 | 4397900% | 4398600% | 15.8388 | 0.63518 | 15.8388 | 9.0064 |  |  |  | 0.020259 | 0.040103 | 0 | 0 |  | 39.8618
0 | 4398600% | 4399300% | 17.0243 | 0.63518 | 17.0243 | 9.6416 |  |  |  | 0.040103 | 0.03731 | 0 | 0 |  | 29.1679
0 | 4399300% | 4400000% | 18.2098 | 0.62966 | 18.2098 | 10.2713 |  |  |  | 0.03731 | 0.034578 | 0 | 0
0 | 4400000% | 4400700% | 19.3977 | 0.60417 | 19.3977 | 10.8755 |  |  |  | 0.034578 | 0.031146 | 0 | 0
0 | 4400700% | 4401400% | 20.5652 | 0.62098 | 20.5652 | 11.4964 |  |  |  | 0.031146 | 0.030196 | 0 | 0
0 | 4401400% | 4402100% | 21.7227 | 0.5837 | 21.7227 | 12.0801 |  |  |  | 0.030196 | 0.02687 | 0 | 0
0 | 4402100% | 4402800% | 22.3298 | 0.57606 | 22.3298 | 12.6562 |  |  |  | 0.02687 | 0.025798 | 0 | 0
0 | 4402800% | 4403500% | 22.8076 | 0.58435 | 22.8076 | 13.2405 |  |  |  | 0.025798 | 0.025621 | 0 | 0
0 | 4403500% | 4404200% | 23.2169 | 0.50043 | 23.2169 | 13.741 |  |  |  | 0.025621 | 0.021554 | 0 | 0
0 | 4404200% | 4404900% | 23.4711 | 0.30116 | 23.4711 | 14.0421 |  |  |  | 0.021554 | 0.012831 | 0 | 0
0 | 4404900% | 4405600% | 23.9491 | 0.57442 | 23.9491 | 14.6165 |  |  |  | 0.012831 | 0.023985 | 0 | 0
0 | 4405600% | 4406300% | 24.4785 | 0.61413 | 24.4785 | 15.2307 |  |  |  | 0.023985 | 0.025088 | 0 | 0
0 | 4406300% | 4407000% | 25.1692 | 0.6582 | 25.1692 | 15.8889 |  |  |  | 0.025088 | 0.026151 | 0 | 0
0 | 4407000% | 4407700% | 25.8902 | 0.6581 | 25.8902 | 16.547 |  |  |  | 0.026151 | 0.025419 | 0 | 0
0 | 4407700% | 4408400% | 26.5668 | 0.64998 | 26.5668 | 17.1969 |  |  |  | 0.025419 | 0.024466 | 0 | 0
0 | 4408400% | 4409100% | 27.1063 | 0.66959 | 27.1063 | 17.8665 |  |  |  | 0.024466 | 0.024702 | 0 | 0
0 | 4409100% | 4409800% | 27.7613 | 0.5884 | 27.7613 | 18.4549 |  |  |  | 0.024702 | 0.021195 | 0 | 0
0 | 4409800% | 4410500% | 28.9432 | 0.78467 | 28.9432 | 19.2396 |  |  |  | 0.021195 | 0.027111 | 0 | 0
0 | 4410500% | 4411200% | 29.4766 | 0.78489 | 29.4766 | 20.0245 |  |  |  | 0.027111 | 0.026628 | 0 | 0
0 | 4411200% | 4411900% | 29.9435 | 0.78476 | 29.9435 | 20.8093 |  |  |  | 0.026628 | 0.026208 | 0 | 0
0 | 4411900% | 4412600% | 30.3499 | 0.77225 | 30.3499 | 21.5815 |  |  |  | 0.026208 | 0.025445 | 0 | 0
0 | 4412600% | 4413300% | 30.4556 | 0.71026 | 30.4556 | 22.2918 |  |  |  | 0.025445 | 0.023321 | 0 | 0
0 | 4413300% | 4414000% | 30.4708 | 0.69874 | 30.4708 | 22.9905 |  |  |  | 0.023321 | 0.022931 | 0 | 0
0 | 4414000% | 4414700% | 30.486 | 0.69834 | 30.486 | 23.6888 |  |  |  | 0.022931 | 0.022907 | 0 | 0
0 | 4414700% | 4415400% | 30.5371 | 0.72684 | 30.5371 | 24.4157 |  |  |  | 0.022907 | 0.023802 | 0 | 0
0 | 4415400% | 4416100% | 30.5887 | 0.62221 | 30.5887 | 25.0379 |  |  |  | 0.023802 | 0.020341 | 0 | 0
0 | 4416100% | 4416800% | 30.6402 | 0.51709 | 30.6402 | 25.555 |  |  |  | 0.020341 | 0.016876 | 0 | 0
0 | 4416800% | 4417500% | 30.6918 | 0.51709 | 30.6918 | 26.0721 |  |  |  | 0.016876 | 0.016848 | 0 | 0
0 | 4417500% | 4418200% | 30.7433 | 0.51709 | 30.7433 | 26.5891 |  |  |  | 0.016848 | 0.016819 | 0 | 0
0 | 4418200% | 4418900% | 30.7949 | 0.48268 | 30.7949 | 27.0718 |  |  |  | 0.016819 | 0.015674 | 0 | 0
0 | 4418900% | 4419600% | 30.8397 | 0.46114 | 30.8397 | 27.533 |  |  |  | 0.015674 | 0.014953 | 0 | 0
0 | 4419600% | 4420300% | 30.8547 | 0.38398 | 30.8547 | 27.917 |  |  |  | 0.014953 | 0.012445 | 0 | 0
0 | 4420300% | 4421000% | 30.8697 | 0.37178 | 30.8697 | 28.2887 |  |  |  | 0.012445 | 0.012044 | 0 | 0
0 | 4421000% | 4421700% | 30.8847 | 0.3916 | 30.8847 | 28.6803 |  |  |  | 0.012044 | 0.01268 | 0 | 0
0 | 4421700% | 4422400% | 30.8998 | 0.34256 | 30.8998 | 29.0229 |  |  |  | 0.01268 | 0.011086 | 0 | 0
0 | 4422400% | 4423100% | 30.9148 | 0.3247 | 30.9148 | 29.3476 |  |  |  | 0.011086 | 0.2 | 0 | 0
0 | 4423100% | 4423800% | 30.9298 | 0.1315 | 30.9298 | 29.4791 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4423800% | 4424500% | 30.9448 | 0.26395 | 30.9448 | 29.743 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4424500% | 4425200% | 30.9598 | 0.52948 | 30.9598 | 30.2725 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4425200% | 4425900% | 30.9748 | 0.036303 | 30.9748 | 30.3088 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4425900% | 4426600% | 30.9898 | 0.036303 | 30.9898 | 30.3451 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4426600% | 4427300% | 31.0048 | 0.036303 | 31.0048 | 30.3814 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4427300% | 4428000% | 31.0198 | 0.036303 | 31.0198 | 30.4177 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4428000% | 4428700% | 31.0348 | 0.036303 | 31.0348 | 30.454 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4428700% | 4429400% | 31.0498 | 0.036303 | 31.0498 | 30.4903 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4429400% | 4430100% | 31.0648 | 0.036303 | 31.0648 | 30.5266 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4430100% | 4430800% | 31.0798 | 0.036303 | 31.0798 | 30.5629 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4430800% | 4431500% | 31.1565 | 0.045818 | 31.1565 | 30.6088 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4431500% | 4432200% | 31.5224 | 0.17397 | 31.5224 | 30.7827 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4432200% | 4432900% | 31.9333 | 0.17397 | 31.9333 | 30.9567 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4432900% | 4433600% | 32.1 | 0.17397 | 32.1 | 31.1307 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4433600% | 4434300% | 32.115 | 0.17397 | 32.115 | 31.3047 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4434300% | 4435000% | 32.13 | 0.17397 | 32.13 | 31.4786 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4435000% | 4435700% | 32.145 | 0.16541 | 32.145 | 31.644 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4435700% | 4436400% | 32.16 | 0.045785 | 32.16 | 31.6898 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4436400% | 4437100% | 32.175 | 0.036303 | 32.175 | 31.7261 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4437100% | 4437800% | 32.19 | 0.036303 | 32.19 | 31.7624 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4437800% | 4438500% | 32.205 | 0.036303 | 32.205 | 31.7987 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4438500% | 4439200% | 32.2201 | 0.036303 | 32.2201 | 31.835 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4439200% | 4439900% | 32.2251 | 0.012101 | 32.2251 | 31.8471 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4439900% | 4440600% | 32.2401 | 0.036303 | 32.2401 | 31.8834 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4440600% | 4441300% | 32.394 | 0.036302 | 32.394 | 31.9197 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4441300% | 4442000% | 32.6089 | 0.036301 | 32.6089 | 31.956 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4442000% | 4442700% | 32.8237 | 0.036301 | 32.8237 | 31.9923 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4442700% | 4443400% | 33.0386 | 0.036301 | 33.0386 | 32.0286 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4443400% | 4444100% | 33.1515 | 0.036301 | 33.1515 | 32.0649 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4444100% | 4444800% | 33.1665 | 0.036301 | 33.1665 | 32.1012 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4444800% | 4445500% | 33.1693 | 0.036301 | 33.1693 | 32.1375 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4445500% | 4446200% | 33.1693 | 0.03025 | 33.1693 | 32.1678 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4446200% | 4446900% | 33.1693 | 0.036301 | 33.1693 | 32.2041 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4446900% | 4447600% | 33.1693 | 0.036301 | 33.1693 | 32.2404 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4447600% | 4448300% | 33.1693 | 0.036301 | 33.1693 | 32.2767 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4448300% | 4449000% | 33.1693 | 0.036301 | 33.1693 | 32.313 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4449000% | 4449700% | 33.1693 | 0.036301 | 33.1693 | 32.3493 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4449700% | 4450400% | 33.1693 | 0.036301 | 33.1693 | 32.3856 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4450400% | 4451100% | 33.1693 | 0.036301 | 33.1693 | 32.4219 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4451100% | 4451800% | 33.1693 | 0.036301 | 33.1693 | 32.4582 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4451800% | 4452500% | 33.1693 | 0.036301 | 33.1693 | 32.4945 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4452500% | 4453200% | 33.3587 | 0.036301 | 33.3587 | 32.5308 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4453200% | 4453900% | 33.9567 | 0.036301 | 33.9567 | 32.5671 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4453900% | 4454600% | 34.5248 | 0.036301 | 34.5248 | 32.6034 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4454600% | 4455300% | 34.5248 | 0.036301 | 34.5248 | 32.6397 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4455300% | 4456000% | 34.5248 | 0.036301 | 34.5248 | 32.676 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4456000% | 4456700% | 34.5248 | 0.036301 | 34.5248 | 32.7123 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4456700% | 4457400% | 34.5248 | 0.036301 | 34.5248 | 32.7486 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4457400% | 4458100% | 34.5248 | 0.036301 | 34.5248 | 32.7849 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4458100% | 4458800% | 34.5248 | 0.036301 | 34.5248 | 32.8212 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4458800% | 4459500% | 34.5248 | 0.036301 | 34.5248 | 32.8575 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4459500% | 4460200% | 34.5248 | 0.036301 | 34.5248 | 32.8938 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4460200% | 4460900% | 34.5248 | 0.036301 | 34.5248 | 32.9301 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4460900% | 4461600% | 34.5248 | 0.036301 | 34.5248 | 32.9664 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4461600% | 4462300% | 34.7454 | 0.036349 | 34.7454 | 33.0027 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4462300% | 4463000% | 35.0273 | 0.036301 | 35.0273 | 33.039 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4463000% | 4463700% | 35.7635 | 0.13249 | 35.7635 | 33.1715 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4463700% | 4464400% | 36.5959 | 0.183 | 36.5959 | 33.3545 |  |  |  | 0.2 | 0.2 | 0 | 0
0 | 4464400% | 4465100% | 37.2204 | 0.183 | 37.2204 | 33.5375 |  |  |  | 0.2 | 1.2 | 0 | 0
0 | 4465100% | 4465800% | 37.6557 | 0.15725 | 37.6557 | 33.6948 |  |  |  | 1.2 | 2.2 | 0 | 0
0 | 4465800% | 4466500% | 38.0169 | 0.16734 | 38.0169 | 33.8621 |  |  |  | 2.2 | 3.2 | 0 | 0
0 | 4466500% | 4467200% | 38.3283 | 0.36381 | 38.3283 | 34.2259 |  |  |  | 3.2 | 4.2 | 0 | 0
0 | 4467200% | 4467900% | 38.6649 | 0.26384 | 38.6649 | 34.4071 |  |  |  | 4.2 | 5.2 | 0 | 0
0 | 4467900% | 4468600% | 38.8416 | 0.20442 | 38.8416 | 34.6115 |  |  |  | 5.2 | 6.2 | 0 | 0
Current | 4468600% | 4469300% | 39.3165 | 0.39526 | 39.3165 | 35.0068
0 | 4469300% | 4470000% | 39.7493 | 0 | 39.7493
0 | 4470000% | 4470700% | 39.8278 | 0 | 39.8278
0 | 4470700% | 4471400% | 39.8618 | 0 | 39.8618
0 | 4471400% |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0 | [10 empty] | 0.72973
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
 | time axis 2020-09-05 to 2022-05-28
[67 empty] | 675601.26 | 538475.55 | 654168.61 | 1180852.09 | 532396.55 | 465880.28 | 405397.43 | 104664.95 | 14250.32 | 14176.54 | 50115.92 | 50538.36 | 50538.36 | 50538.36 | 50538.36 | 50538.36 | 43838.61 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 75693.82 | 364910.91 | 409826.63 | 165723.9 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 4664.75 | 13994.24 | 152967.87 | 213830.09 | 213830.09 | 213830.09 | 111957.83 | 13994.24 | 13994.24 | 11661.87 | 13994.24 | 13994.24 | 13994.24 | 13994.24 | 5177.87 |  |  |  |  | 189368.19 | 598004.82 | 568104.58 | [10 empty] | 183734.46 | 244968.1 | 717236.84 | 903178.45 | 695312.01 | 461968.56 | 372978.38 | 323094.21 | 361019.94 | 168523.4 | 545685.21 | 495564.05 | 41525.03 | 12085.1
[67 empty] | 26355383.05 | 26893858.6 | 27548027.2 | 28728879.29 | 29261275.84 | 29727156.11 | 30132553.54 | 30237218.49 | 30251468.81 | 30265645.34 | 30315761.27 | 30366299.63 | 30416837.99 | 30467376.35 | 30517914.72 | 30568453.08 | 30612291.68 | 30626285.93 | 30640280.17 | 30654274.42 | 30668268.66 | 30682262.9 | 30696257.15 | 30710251.39 | 30724245.64 | 30738239.88 | 30752234.13 | 30766228.37 | 30780222.61 | 30794216.86 | 30808211.1 | 30822205.35 | 30836199.59 | 30911893.41 | 31276804.32 | 31686630.95 | 31852354.85 | 31866349.09 | 31880343.34 | 31894337.58 | 31908331.82 | 31922326.07 | 31936320.31 | 31950314.56 | 31964308.8 | 31968973.55 | 31982967.79 | 32135935.66 | 32349765.75 | 32563595.84 | 32777425.93 | 32889383.76 | 32903378.01 | 32917372.25 | 32929034.12 | 32943028.37 | 32957022.61 | 32971016.85 | 32985011.1 | 32990188.97 | 32990188.97 | 32990188.97 | 32990188.97 | 32990188.97 | 33179557.16 | 33777561.99 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34345666.57 | 34529401.03 | 34774369.12 | 35491605.96 | 36394784.41 | 37090096.42 | 37552064.98 | 37925043.36 | 38248137.57 | 38609157.51 | 38777680.91 | 39323366.12 | 39818930.18 | 39860455.21 | 39872540.31
[67 empty] | 26.3554 | 26.8939 | 27.548 | 28.7289 | 29.2613 | 29.7272 | 30.1326 | 30.2372 | 30.2515 | 30.2656 | 30.3158 | 30.3663 | 30.4168 | 30.4674 | 30.5179 | 30.5685 | 30.6123 | 30.6263 | 30.6403 | 30.6543 | 30.6683 | 30.6823 | 30.6963 | 30.7103 | 30.7242 | 30.7382 | 30.7522 | 30.7662 | 30.7802 | 30.7942 | 30.8082 | 30.8222 | 30.8362 | 30.9119 | 31.2768 | 31.6866 | 31.8524 | 31.8663 | 31.8803 | 31.8943 | 31.9083 | 31.9223 | 31.9363 | 31.9503 | 31.9643 | 31.969 | 31.983 | 32.1359 | 32.3498 | 32.5636 | 32.7774 | 32.8894 | 32.9034 | 32.9174 | 32.929 | 32.943 | 32.957 | 32.971 | 32.985 | 32.9902 | 32.9902 | 32.9902 | 32.9902 | 32.9902 | 33.1796 | 33.7776 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.5294 | 34.7744 | 35.4916 | 36.3948 | 37.0901 | 37.5521 | 37.925 | 38.2481 | 38.6092 | 38.7777 | 39.3234 | 39.8189 | 39.8605 | 39.8725
[67 empty] | 26.3554 | 26.8939 | 27.548 | 28.7289 | 29.2613 | 29.7272 | 30.1326 | 30.2372 | 30.2515 | 30.2656 | 30.3158 | 30.3663 | 30.4168 | 30.4674 | 30.5179 | 30.5685 | 30.6123 | 30.6263 | 30.6403 | 30.6543 | 30.6683 | 30.6823 | 30.6963 | 30.7103 | 30.7242 | 30.7382 | 30.7522 | 30.7662 | 30.7802 | 30.7942 | 30.8082 | 30.8222 | 30.8362 | 30.9119 | 31.2768 | 31.6866 | 31.8524 | 31.8663 | 31.8803 | 31.8943 | 31.9083 | 31.9223 | 31.9363 | 31.9503 | 31.9643 | 31.969 | 31.983 | 32.1359 | 32.3498 | 32.5636 | 32.7774 | 32.8894 | 32.9034 | 32.9174 | 32.929 | 32.943 | 32.957 | 32.971 | 32.985 | 32.9902 | 32.9902 | 32.9902 | 32.9902 | 32.9902 | 33.1796 | 33.7776 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.3457 | 34.5294 | 34.7744 | 35.4916 | 36.3948 | 37.0901 | 37.5521 | 37.925 | 38.2481 | 38.6092 | 38.7777 | 39.3234 | 39.8189 | 39.8605 | 39.8725
Formulas:
This Report Date = IF([This Report Date, row above]>Timeline[Forecast End Date],"",WORKDAY.INTL([Last Report Date],4,7,))
Date = IFERROR(IF([Date, row above]>Timeline[Forecast End Date],"",EOMONTH([Date, row above],1)),"")
Note on S32: MME: Under approval
Note on S33: MME: Under approval
Note on S34: MME: Under approval
Note on S35: MME: Under approval
Note on S36: MME: Under approval
Note on S37: MME: Under approval

## VA Output
|  |  | 85.68% | 86.87%
|  | Report Week Date | 100% | 100%
0.2834 | -0.7166 | 2022-05-12 |  |  | Last Week Variance | This Week Variance
0.2905 | -0.7095 |  |  | Construction | -8.784% | -9.437%
0.2975 | -0.7025 |  |  | Procurement | 0% | 0%
|  |  |  | Engineering | 0% | 0%
|  | 112 |  | Prelims | -13.13% | -14.32%
|  |  |  | Overall Variance | -100% | -100%
[11 empty] | 0.607 | 0.607
|  | Date | Construction Variance | Procurement Variance | Engineering Variance | Prelims Variance | Overall Planned | Overall Actual | Overall Variance
| 0 | 2019-06-23 | 0% | -6% | -0.8677% | -0.5378% | 0% | 0% | 0%
| 0 | 2019-06-27 | -0.001634% | -16% | -1.404% | -0.2255% | 0.3934% | 0.06157% | -0.3318%
| 0 | 2019-07-04 | -0.003592% | -26% | -1.404% | -0.5779% | 0.8751% | 0.137% | -0.7381%
| 0 | 2019-07-11 | -0.005543% | -36% | -1.394% | -0.8492% | 1.357% | 0.2123% | -1.144%
| 0 | 2019-07-18 | -0.007741% | -46% | -0.6192% | -1.346% | 1.886% | 0.3262% | -1.56% | -61.69%
| 0 | 2019-07-25 | -0.00992% | -56% | 0.7593% | -1.828% | 2.467% | 0.4822% | -1.985%
| 0 | 2019-08-01 | -0.01484% | -66% | 2.113% | -2.335% | 3.043% | 0.6608% | -2.382%
| 0 | 2019-08-08 | -0.02047% | -76% | 3.085% | -3.361% | 3.571% | 0.7908% | -2.78% | 0%
| 0 | 2019-08-15 | -0.02173% | -85.53% | 3.116% | -4.955% | 3.699% | 0.8141% | -2.884%
| 0 | 2019-08-22 | -0.03527% | -94.14% | 2.787% | -6.089% | 4.521% | 1% | -3.52%
| 0 | 2019-08-29 | -0.05853% | -96.74% | 0.9994% | -6.863% | 5.42% | 1.252% | -4.168% | -32.3%
| 0 | 2019-09-05 | -0.1883% | 4.614% | 1.135% | -11.28% | 6.748% | 1.85% | -4.897%
| 0 | 2019-09-12 | -0.3913% | 6.179% | 1.208% | -18.35% | 8.255% | 2.611% | -5.644%
| 0 | 2019-09-19 | -0.3744% | 7.847% | 1.282% | -25.18% | 9.481% | 3.415% | -6.067% | -0.43%
| 0 | 2019-09-26 | -0.1625% | 9.236% | 1.821% | -31.84% | 10.13% | 3.85% | -6.278%
| 0 | 2019-10-03 | -0.1898% | 10.9% | 2.457% | -38.26% | 10.9% | 4.149% | -6.756%
| 0 | 2019-10-10 | -0.2168% | 12.57% | 5.24% | -44.37% | 11.68% | 4.448% | -7.234%
| 0 | 2019-10-17 | -0.244% | 14.24% | 6.252% | -46.23% | 12.46% | 4.748% | -7.713%
| 0 | 2019-10-24 | -0.2712% | 15.91% | 6.41% | -49.71% | 13.22% | 5.048% | -8.176%
| 0 | 2019-10-31 | -0.2984% | 17.57% | 6.641% | -50.67% | 13.97% | 5.348% | -8.62%
| 0 | 2019-11-07 | -0.3256% | 19.24% | 7.669% | -51.7% | 14.71% | 5.647% | -9.065%
| 0 | 2019-11-14 | -0.3511% | 20.91% | 9.645% | -52.72% | 15.46% | 5.947% | -9.508%
| 0 | 2019-11-21 | -0.2747% | 22.58% | 9.99% | -53.75% | 16.12% | 6.248% | -9.869%
| 0 | 2019-11-28 | -0.1983% | 24.25% | 15.02% | -54.77% | 16.78% | 6.549% | -10.23%
| 0 | 2019-12-05 | -0.1358% | 25.91% | 20.11% | -55.76% | 17.45% | 6.845% | -10.6%
| 0 | 2019-12-12 | -0.1401% | 27.58% | 24.49% | -56.69% | 18.13% | 7.096% | -11.03%
| 0 | 2019-12-19 | -0.1364% | 29.25% | 32.92% | -57.38% | 18.8% | 7.347% | -11.46%
| 0 | 2019-12-26 | -0.1326% | 30.92% | 36.75% | -57.11% | 19.46% | 7.587% | -11.87%
| 0 | 2020-01-02 | -0.1289% | 32.58% | 40.26% | -56.76% | 19.85% | 7.821% | -12.03%
| 0 | 2020-01-09 | -0.1252% | 34.25% | 47.73% | -56.55% | 20.03% | 8.056% | -11.98%
| 0 | 2020-01-16 | -0.1286% | 35.92% | 54.13% | -56.34% | 20.26% | 8.325% | -11.93%
| 0 | 2020-01-23 | -0.1701% | 37.59% | 60.36% | -56.13% | 20.58% | 8.689% | -11.89%
| 0 | 2020-01-30 | -0.1632% | 39.26% | 64.25% | -55.92% | 20.83% | 9.034% | -11.8%
| 0 | 2020-02-06 | -0.1782% | 40.93% | 73.8% | -55.71% | 21% | 9.287% | -11.71%
| 0 | 2020-02-13 | -0.2141% | 42.59% | 80.65% | -55.32% | 21.34% | 9.681% | -11.66%
| 0 | 2020-02-20 | -0.4536% | 44.26% | 88.56% | -54.81% | 22.41% | 10.63% | -11.77%
| 0 | 2020-02-27 | -0.5878% | 45.93% | 89.97% | -54.47% | 23.82% | 12% | -11.83%
| 0 | 2020-03-05 | -0.44% | 47.6% | 90.6% | -54% | 24.61% | 12.95% | -11.66%
| 0 | 2020-03-12 | -0.3377% | 49.26% | 91.55% | -53.22% | 24.93% | 13.41% | -11.52%
| 0 | 2020-03-19 | -0.3627% | 50.93% | 94.76% | -52.91% | 25.18% | 13.68% | -11.5%
| 0 | 2020-03-26 | -0.3685% | 52.6% | 94.78% | -52.61% | 25.4% | 13.95% | -11.45%
| 0 | 2020-04-02 | -0.3627% | 54.27% | 94.78% | -52.3% | 25.59% | 14.21% | -11.37%
| 0 | 2020-04-09 | -0.9141% | 55.93% | 94.78% | -51.99% | 26.24% | 14.65% | -11.59%
| 0 | 2020-04-16 | -0.4886% | 57.6% | 94.78% | -51.93% | 26.28% | 15.21% | -11.07%
| 0 | 2020-04-23 | -0.2347% | 59.21% | 94.78% | -51.92% | 26.32% | 15.62% | -10.7%
| 0 | 2020-04-30 | -0.1278% | 60.54% | 94.78% | -52.08% | 26.35% | 15.87% | -10.48%
| 0 | 2020-05-07 | -0.985% | 61.86% | 96.38% | -52.24% | 27.92% | 16.89% | -11.03%
| 0 | 2020-05-14 | -3.143% | 63.18% | 97.04% | -52.4% | 31.48% | 18.87% | -12.61%
| 0 | 2020-05-21 | -5.783% | 64.5% | 97.04% | -52.57% | 34.95% | 20.36% | -14.58%
| 0 | 2020-05-28 | -7.154% | 65.33% | 97.04% | -53.01% | 36.71% | 21.11% | -15.6%
| 0 | 2020-06-04 | -9.161% | 66.98% | 97.04% | -53% | 39.73% | 22.7% | -17.03%
| 0 | 2020-06-11 | -11.1% | 68.63% | 97.04% | -52.99% | 42.71% | 24.3% | -18.41%
| 0 | 2020-06-18 | -13.04% | 70.28% | 97.04% | -53.06% | 45.68% | 25.88% | -19.8%
| 0 | 2020-06-25 | -14.98% | 71.93% | 97.04% | -53.1% | 48.66% | 27.4% | -21.26%
| 0 | 2020-07-02 | -16.79% | 73.58% | 97.04% | 47.54% | 51.59% | 28.96% | -22.63%
| 0 | 2020-07-09 | -18.68% | 75.23% | 97.04% | 48.18% | 54.5% | 30.43% | -24.07%
| 0 | 2020-07-16 | -18.87% | 76.88% | 97.04% | 48.82% | 56.02% | 31.88% | -24.14%
| 0 | 2020-07-23 | -18.63% | 78.53% | 97.04% | 49.46% | 57.22% | 33.34% | -23.87%
| 0 | 2020-07-30 | -18.42% | 79.64% | 97.61% | 49.99% | 58.24% | 34.6% | -23.64%
| 0 | 2020-08-06 | -18.32% | 80.74% | 98.18% | 50.31% | 58.88% | 35.36% | -23.52%
| 0 | 2020-08-13 | -18.11% | 82.39% | 98.2% | 50.95% | 60.08% | 36.8% | -23.28%
| 0 | 2020-08-20 | -17.94% | 84.04% | 98.22% | 51.59% | 61.41% | 38.35% | -23.06%
| 0 | 2020-08-27 | -18.18% | 85.69% | 98.25% | 52.23% | 63.14% | 40% | -23.14%
| 0 | 2020-09-03 | -18.5% | 87.34% | 98.27% | 52.81% | 64.95% | 41.65% | -23.3%
| 0 | 2020-09-10 | -18.71% | 88.99% | 98.29% | 53.27% | 66.65% | 43.29% | -23.36%
| 0 | 2020-09-17 | -18.42% | 90.64% | 98.31% | 53.73% | 68% | 44.97% | -23.03%
| 0 | 2020-09-24 | -18.72% | 92.02% | 98.33% | 54.06% | 69.64% | 46.45% | -23.2%
| 0 | 2020-10-01 | -20.07% | 93.67% | 98.35% | 54.45% | 72.61% | 48.42% | -24.19%
| 0 | 2020-10-08 | -19.39% | 95.32% | 98.37% | 54.83% | 73.95% | 50.39% | -23.56%
| 0 | 2020-10-15 | -18.49% | 96.97% | 98.4% | 55.21% | 75.12% | 52.36% | -22.76%
| 0 | 2020-10-22 | -17.45% | 98.62% | 98.42% | 55.59% | 76.14% | 54.3% | -21.83%
| 0 | 2020-10-29 | -15.65% | 100% | 98.44% | 55.98% | 76.4% | 56.09% | -20.32%
| 0 | 2020-11-05 | -13.59% | 0% | 98.46% | 56.36% | 76.44% | 57.84% | -18.6%
| 0 | 2020-11-12 | -11.52% | 0% | 98.49% | 56.74% | 76.48% | 59.6% | -16.88%
| 0 | 2020-11-19 | -9.48% | 0% | 98.51% | 57.12% | 76.61% | 61.42% | -15.18%
| 0 | 2020-11-26 | -7.768% | 0% | 98.53% | 57.51% | 76.74% | 62.99% | -13.75%
| 0 | 2020-12-03 | -6.387% | 0% | 98.55% | 57.89% | 76.87% | 64.29% | -12.58%
| 0 | 2020-12-10 | -5.005% | 0% | 98.57% | 58.27% | 77% | 65.59% | -11.41%
| 0 | 2020-12-17 | -3.624% | 0% | 98.6% | 58.65% | 77.12% | 66.89% | -10.24%
| 0 | 2020-12-24 | -2.35% | 0% | 98.62% | 59.04% | 77.25% | 68.1% | -9.153%
| 0 | 2020-12-31 | -1.124% | 0% | 98.64% | 59.42% | 77.37% | 69.26% | -8.105%
| 0 | 2021-01-07 | -0.04558% | 0% | 98.66% | 59.8% | 77.4% | 70.23% | -7.177%
| 0 | 2021-01-14 | 0.9941% | 0% | 98.68% | 60.18% | 77.44% | 71.16% | -6.279%
| 0 | 2021-01-21 | 2.096% | 0% | 98.71% | 60.56% | 77.48% | 72.15% | -5.332%
| 0 | 2021-01-28 | 3.044% | 0% | 98.73% | 60.95% | 77.52% | 73.01% | -4.507%
| 0 | 2021-02-04 | 3.936% | 0% | 98.75% | 61.33% | 100% | 73.83% | -26.17%
| 0 | 2021-02-11 | 4.22% | 0% | 98.77% | 61.71% | 100% | 74.16% | -25.84%
| 0 | 2021-02-18 | 4.921% | 0% | 99.49% | 62.09% | 100% | 74.83% | -25.17%
| 0 | 2021-02-25 | 6.456% | 0% | 99.51% | 62.48% | 100% | 76.16% | -23.84%
| 0 | 2021-03-04 | 6.441% | 0% | 99.53% | 62.86% | 100% | 76.25% | -23.75%
| 0 | 2021-03-11 | 6.427% | 0% | 99.56% | 63.24% | 100% | 76.34% | -23.66%
| 0 | 2021-03-18 | 6.412% | 0% | 99.58% | 63.62% | 100% | 76.44% | -23.56%
| 0 | 2021-03-25 | -71.66% | 0% | -32.3% | -31.4% | 100% | 76.53% | -23.47%
| 0 | 2021-04-01 | -70.95% | 0% | -32.3% | -30.9% | 100% | 76.63% | -23.37%
| 0 | 2021-04-08 | -70.25% | 0% | -27.63% | -30.4% | 100% | 76.72% | -23.28%
| 0 | 2021-04-15 | 0% | 0% | 99.67% | 65.15% | 100% | 76.81% | 0%
| 0 | 2021-04-22 | 6.339% | 0% | 99.69% | 65.54% | 100% | 76.91% | -23.09%
| 0 | 2021-04-29 | 6.16% | 0% | 99.71% | 65.92% | 100% | 77.02% | -22.98% | 65.67
| 0 | 2021-05-06 | 5.475% | 0% | 99.73% | 66.3% | 100% | 77.46% | -22.54% | -64.67
| 0 | 2021-05-13 | 4.649% | 0% | 99.76% | 66.68% | 100% | 77.9% | -22.1%
| 0 | 2021-05-20 | 4.59% | 0% | 99.78% | 67.07% | 100% | 78.34% | -21.66%
| 0 | 2021-05-27 | 5.008% | 0% | 99.8% | 67.45% | 100% | 78.78% | -21.22%
| 0 | 2021-06-03 | 5.426% | 0% | 99.82% | 67.83% | 100% | 79.22% | -20.78%
| 0 | 2021-06-10 | 5.817% | 0% | 99.84% | 68.21% | 100% | 79.64% | -20.36%
| 0 | 2021-06-17 | 5.832% | 0% | 99.87% | 68.6% | 100% | 79.76% | -20.24%
| 0 | 2021-06-24 | 5.817% | 0% | 99.89% | 68.98% | 100% | 79.85% | -20.15%
| 0 | 2021-07-01 | 5.803% | 0% | 99.91% | 69.36% | 100% | 79.94% | -20.06%
| 0 | 2021-07-08 | 5.788% | 0% | 99.93% | 69.74% | 100% | 80.04% | -19.96%
| 0 | 2021-07-15 | 5.773% | 0% | 99.96% | 70.13% | 100% | 80.13% | -19.87%
| 0 | 2021-07-22 | 5.768% | 0% | 99.96% | 70.25% | 100% | 80.16% | -19.84%
| 0 | 2021-07-29 | 5.754% | 0% | 99.99% | 70.64% | 100% | 80.26% | -19.74%
| 0 | 2021-08-05 | 5.302% | 0% | 100% | 71.02% | 100% | 80.35% | -19.65%
| 0 | 2021-08-12 | 4.66% | 0% | 0% | 71.4% | 100% | 80.44% | -19.56%
| 0 | 2021-08-19 | 4.017% | 0% | 0% | 71.78% | 100% | 80.54% | -19.46%
| 0 | 2021-08-26 | 3.374% | 0% | 0% | 72.17% | 100% | 80.63% | -19.37%
| 0 | 2021-09-02 | 3.051% | 0% | 0% | 72.55% | 100% | 80.73% | -19.27%
| 0 | 2021-09-09 | 3.037% | 0% | 0% | 72.93% | 100% | 80.82% | -19.18%
| 0 | 2021-09-16 | 3.061% | 0% | 0% | 73.31% | 100% | 80.91% | -19.09%
| 0 | 2021-09-23 | 3.088% | 0% | 0% | 73.63% | 100% | 80.99% | -19.01%
| 0 | 2021-09-30 | 3.12% | 0% | 0% | 74.01% | 100% | 81.09% | -18.91%
| 0 | 2021-10-07 | 3.153% | 0% | 0% | 74.4% | 100% | 81.18% | -18.82%
| 0 | 2021-10-14 | 3.185% | 0% | 0% | 74.78% | 100% | 81.27% | -18.73%
| 0 | 2021-10-21 | 3.218% | 0% | 0% | 75.16% | 100% | 81.37% | -18.63%
| 0 | 2021-10-28 | 3.25% | 0% | 0% | -24.46% | 100% | 81.46% | -18.54%
| 0 | 2021-11-04 | 3.283% | 0% | 0% | -24.07% | 100% | 81.56% | -18.44%
| 0 | 2021-11-11 | 3.315% | 0% | 0% | -23.69% | 100% | 81.65% | -18.35%
| 0 | 2021-11-18 | 3.347% | 0% | 0% | -23.31% | 100% | 81.74% | -18.26%
| 0 | 2021-11-25 | 3.38% | 0% | 0% | -22.93% | 100% | 81.84% | -18.16%
| 0 | 2021-12-02 | 2.817% | 0% | 0% | -22.54% | 100% | 81.93% | -18.07%
| 0 | 2021-12-09 | 0.9702% | 0% | 0% | -22.16% | 100% | 82.02% | -17.98%
| 0 | 2021-12-16 | -0.7828% | 0% | 0% | -21.78% | 100% | 82.12% | -17.88%
| 0 | 2021-12-23 | -0.7503% | 0% | 0% | -21.4% | 100% | 82.21% | -17.79%
| 0 | 2021-12-30 | -0.7178% | 0% | 0% | -21.01% | 100% | 82.31% | -17.69%
| 0 | 2022-01-06 | -0.6854% | 0% | 0% | -20.63% | 100% | 82.4% | -17.6%
| 0 | 2022-01-13 | -0.6529% | 0% | 0% | -20.25% | 100% | 82.49% | -17.51%
| 0 | 2022-01-20 | -0.6204% | 0% | 0% | -19.87% | 100% | 82.59% | -17.41%
| 0 | 2022-01-27 | -0.588% | 0% | 0% | -19.48% | 100% | 82.68% | -17.32%
| 0 | 2022-02-03 | -0.5555% | 0% | 0% | -19.1% | 100% | 82.78% | -17.22%
| 0 | 2022-02-10 | -0.523% | 0% | 0% | 81.28% | 100% | 82.87% | -17.13%
| 0 | 2022-02-17 | -0.4905% | 0% | 0% | 81.66% | 100% | 82.96% | -17.04%
| 0 | 2022-02-24 | -0.4581% | 0% | 0% | -6.11% | 100% | 83.06% | -16.94%
| 0 | 2022-03-03 | -1.003% | 0% | 0% | -7.009% | 100% | 83.15% | -16.85%
| 0 | 2022-03-10 | -1.74% | 0% | 0% | -7.908% | 100% | 83.24% | -16.76%
| 0 | 2022-03-17 | -3.6% | 0% | 0% | -8.807% | 100% | 83.58% | -16.42%
| 0 | 2022-03-24 | -5.599% | 0% | 0% | -9.706% | 100% | 84.05% | -15.95%
| 0 | 2022-03-31 | -6.945% | 0% | 0% | -10.61% | 100% | 84.52% | -15.48%
| 0 | 2022-04-07 | -7.771% | 0% | 0% | -11.21% | 100% | 84.9% | -15.1%
| 0 | 2022-04-14 | -8.361% | 0% | 0% | -11.75% | 100% | 0% | -100%
| 0 | 2022-04-21 | -8.815% | 0% | 0% | -12.29% | 100% | 0% | -100%
| 0 | 2022-04-28 | -8.978% | 0% | 0% | -12.83% | 100% | 0% | -100%
| 0 | 2022-05-05 | -8.784% | 0% | 0% | -13.13% | 100% | 0% | -100%
| Current | 2022-05-12 | -9.437% | 0% | 0% | -14.32% | 100% | 0% | -100%
| 0 | 2022-05-19 | -99.83% | 0% | 0% | -100% | 100% | Budgeted Units | #VALUE!
| 0 | 2022-05-26 | -99.96% | 0% | 0% | #REF! | 100% | --- | #VALUE!
| 0 |  | -100% | 0% | 0% | 0% | 100% | --- | #VALUE!
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | Budgeted Total Cost | #VALUE!
| 0 |  | 0% | 0% | 0% | 0% | 100% | 3986177900% | 3986177800%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 3986177900% | 3986177800%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%
| 0 |  | 0% | 0% | 0% | 0% | 100% | 0% | -100%